## Issue Navigator
T | Project | Key | Summary | Labels | P | Created | Worklog Date | Worklog Description | Worklog User | Worklog Account | Worklog Activity | Worked (h)
Task | Beem for Business | BFB-99 | Roadmap to lauch beem4biz.com | mvp, validation | Medium | 2016-01-04 16:38 | 2016-01-06 16:38 | Outlining the strategy for launch | dalia | WebsiteOnDemand | Landing Page | 57
Sub-task | Beem for Business | BFB-115 | Video feed | mvp | Medium | 2016-01-04 16:38 | 2016-01-08 16:38 | Building video streaming framework | dalia | CloudMaint | Landing Page | 35
Sub-task | Beem for Business | BFB-114 | "React" feature | mvp | Medium | 2016-01-04 16:38 | 2016-01-09 16:38 | Simple implementation of "react" feature | dalia | WebsiteOnDemand | Landing Page | 2
Sub-task | Beem for Business | BFB-110 | Copy for email campaigns | web | Medium | 2016-01-04 16:37 | 2016-01-11 16:37 | First drafts of email copy | whitney | CloudMaint | Landing Page | 4
Task | Beem for Business | BFB-109 | Plan the email campaigns | web | Medium | 2016-01-04 16:37 | 2016-08-03 | Working on email campaign wording | whitney | CloudMaint | Landing Page | 57
Task | Beem for Business | BFB-107 | Collect feedback via email | web | Medium | 2016-01-04 16:37 | 2016-01-04 16:38 | Ongoing effort… | dalia | CloudMaint | Validation | 35
Sub-task | Beem for Business | BFB-99 | Website layout | web | Medium | 2016-01-04 16:25 | 2016-01-04 16:38 | Meeting with designers | casey | CloudMaint | Landing Page | 12
Sub-task | Beem for Business | BFB-97 | First mockup | web | Medium | 2016-01-04 16:25 | 2016-01-04 16:38 | Meeting with designers, discussing first mockups | casey | CloudMaint | Android App | 24
Sub-task | Beem for Business | BFB-96 | Brand color scheme | web | Medium | 2016-01-04 16:24 | 2016-01-04 16:37 | meeting with designers, discussing color schemes | casey | CloudMaint | Landing Page | 3
Sub-task | Beem for Business | BFB-38 | Historical analysis | validation | Low | 2016-01-04 16:23 | 2016-08-17 | Researching archived online content about the target market | casey | CloudMaint | Landing Page | 40
Sub-task | Beem for Business | BFB-37 | Online research | validation | Medium | 2016-01-04 16:23 | 2016-08-17 | narrowing down the list of potential research methods | casey | CloudMaint | Validation | 32
Sub-task | Beem for Business | BFB-36 | Phone interviews | validation | Low | 2016-01-04 16:22 | 2016-05-25 | Purchasing relevant phone database and merging with our own existing database | casey | CloudMaint | Validation | 45
Sub-task | Beem for Business | BFB-36 | Phone interviews | validation | Medium | 2016-01-04 16:22 | 2016-05-26 | Conducting phone interviews, using the previously purchased database | casey | CloudMaint | Validation | 100.57
Sub-task | Beem for Business | BFB-35 | In person interviews | validation | High | 2016-01-04 16:21 | 2016-05-17 | In-person customer interviews conducted among the previously signed-up users. | levente | WebsiteOnDemand | Validation | 16
Task | Beem for Business | BFB-30 | Set up FB group for beta testers | CRM, marketing, validation | Medium | 2016-09-21 16:26 | 2016-08-17 | Registering account, uploading profile data | levente | WebsiteOnDemand | Validation | 40
Task | Beem for Business | BFB-30 | Set up FB group for beta testers | CRM, marketing, validation | Medium | 2016-01-04 16:08 | 2016-08-18 | Setting up group for beta testers, building out network on FB | whitney | WebsiteOnDemand | Landing Page | 22
Story | Beem for Business | BFB-27 | Set up Mailchimp | CRM, marketing | Medium | 2016-01-04 16:08 | 2016-08-01 | Creating Mailchimp account | whitney | WebsiteOnDemand | Landing Page | 0.55
Story | Beem for Business | BFB-27 | Set up Mailchimp | CRM, marketing | Medium | 2016-01-04 16:07 | 2016-08-03 | Creating campaigns, campaign workflows | jason | WebsiteOnDemand | Landing Page | 1
Story | Beem for Business | BFB-27 | Set up Mailchimp | CRM, marketing | Medium | 2016-01-04 16:07 | 2016-08-04 | Meeting with UI team to decide on Mailchimp letter templates | jason | WebsiteOnDemand | Landing Page | 0.87
Story | Beem for Business | BFB-27 | Set up Mailchimp | CRM, marketing | Medium | 2016-01-04 16:07 | 2016-08-05 | Setting up automatic reporting from Mailchimp for management | jason | CloudMaint | Landing Page | 3
Story | Beem for Business | BFB-27 | Set up Mailchimp | CRM, marketing | Medium | 2016-01-04 16:07 | 2016-08-10 | Campaign copywriting | jason | CloudMaint | Landing Page | 21.8
Story | Beem for Business | BFB-27 | Set up Mailchimp | CRM, marketing | Medium | 2016-01-04 16:06 | 2016-01-26 | did some great copywriting work | jason | CloudMaint | Landing Page | 45
Story | Beem for Business | BFB-27 | Set up Mailchimp | CRM, marketing | Medium | 2016-01-04 16:06 | 2016-01-26 | analyizing click data | whitney | CloudMaint | Landing Page | 34
Story | Beem for Business | BFB-26 | Set up Hootsuite account | CRM, marketing | Medium | 2016-01-04 16:06 |  |  | whitney | CloudMaint | Landing Page | 4
Sub-task | Beem for Business | BFB-24 | Video feed | DEV, IT | Medium | 2016-01-04 16:05 | 2016-06-16 |  | whitney | CloudMaint | Android App | 59.2
Sub-task | Beem for Business | BFB-24 | Video feed | DEV, IT | Medium | 2016-01-04 16:05 | 2016-12-16 |  | whitney | CloudMaint | Landing Page | 80
Sub-task | Beem for Business | BFB-23 | Video sharing feature | DEV, IT | Medium | 2016-01-04 15:52 |  |  | whitney | CloudMaint | Android App | 2
Sub-task | Beem for Business | BFB-22 | Video recording feature | DEV, IT | Medium | 2016-01-04 15:52 | 2016-05-30 |  | bob | CloudMaint | Android App | 83
Story | Beem for Business | BFB-21 | Implement MVP functions for app | DEV, IT | Medium | 2016-01-04 15:51 | 2016-05-11 | Implementation and feature testing for features: sign-up, login, video uploading, video streaming | bob | CloudMaint | Android App | 80
Sub-task | Beem for Business | BFB-20 | Log-in form | DEV, IT | Medium | 2016-01-04 15:51 | 2016-05-12 |  | bob | CloudMaint | Android App | 10
Sub-task | Beem for Business | BFB-19 | Sign-up form | DEV, IT | Medium | 2016-01-04 15:50 | 2016-06-23 |  | bob | WebsiteOnDemand | Android App | 11
Sub-task | Beem for Business | BFB-18 | Tutorial section | DEV, IT | Medium | 2016-01-04 15:50 | 2016-05-17 |  | bob | WebsiteOnDemand | Android App | 0.5
Task | Beem for Business | BFB-17 | Set up cloud hosting | DEV, IT | Medium | 2016-05-11 11:57 | 2016-05-18 |  | levente | WebsiteOnDemand | Android App | 1.25
Task | Beem for Business | BFB-16 | Set up Dev Environment | DEV, IT | Low | 2016-05-11 11:56 | 2016-08-18 | Registering account with Gitlab.com | levente | WebsiteOnDemand | Android App | 1.5
Task | Beem for Business | BFB-16 | Set up Dev Environment | DEV, IT | High | 2016-05-11 11:55 | 2016-08-31 | Private repo created on Gitlab.com | levente | WebsiteOnDemand | Landing Page | 0.58
Task | Beem for Business | BFB-16 | Set up Dev Environment | DEV, IT | Medium | 2016-01-04 16:24 | 2016-09-08 | Workflows created and configured on Gitlab.com repositories | dalia | WebsiteOnDemand | Landing Page | 5
Task | Beem for Business | BFB-15 | Set up DB | DEV, IT | Medium | 2016-01-04 16:23 | 2016-12-07 | Installing and configuring MySQL database | dalia | WebsiteOnDemand | Android App | 2
Task | Beem for Business | BFB-14 | Create landing page | validation, web | Medium | 2016-01-04 16:23 | 2016-08-17 | Developing landing page, image viewer, sign-up feature | dalia | WebsiteOnDemand | Landing Page | 4
Sub-task | Beem for Business | BFB-13 | Decision on landing page design | web | Medium | 2016-01-03 16:22 |  |  | dalia | WebsiteOnDemand | Landing Page | 3
Sub-task | Beem for Business | BFB-12 | A/B test landing page | web | Medium | 2016-01-04 16:22 | 2016-09-05 | Creating Unbounce account | casey | WebsiteOnDemand | Landing Page | 24
Sub-task | Beem for Business | BFB-12 | A/B test landing page | web | Medium | 2016-01-04 16:21 | 2016-09-07 | Creating landing page versions for testing with different copy language | casey | WebsiteOnDemand | Landing Page | 3
Sub-task | Beem for Business | BFB-12 | A/B test landing page | web | Medium | 2016-09-21 16:26 | 2016-09-08 | Testing landing page with 2 versions | casey | WebsiteOnDemand | Landing Page | 6
Sub-task | Beem for Business | BFB-11 | Landing page copy | billable, validation, web | Medium | 2016-01-04 16:08 | 2016-06-01 | Copy writing for the final landing page | jason | WebsiteOnDemand | Landing Page | 32
Sub-task | Beem for Business | BFB-11 | Landing page copy | billable, validation, web | Medium | 2016-01-04 16:08 | 2016-06-03 | More copy for the landing page, corrected after meeting with UI experts | jason | WebsiteOnDemand | Landing Page | 100.57
Sub-task | Beem for Business | BFB-10 | Design Feedback (3.) | user-experience, user-interface | Medium | 2016-01-23 16:07 | 2016-09-07 |  | jason | WebsiteOnDemand | Android App | 5
Sub-task | Beem for Business | BFB-9 | Design Feedback (2.) | user-experience, user-interface | Medium | 2016-01-04 16:07 | 2016-09-07 |  | jason | WebsiteOnDemand | Android App | 16
Sub-task | Beem for Business | BFB-8 | Design Feedback (1.) | interactions, user-experience, user-interface | Medium | 2016-01-11 16:07 | 2016-05-06 | Checked with the client, sent out calendar invitations for the meeting | jason | WebsiteOnDemand | Android App | 40
Sub-task | Beem for Business | BFB-8 | Design Feedback (1.) | interactions, user-experience, user-interface | Low | 2016-01-04 16:07 | 2016-05-09 | Finalizing the agenda, securing meeting room and equipment | jason | WebsiteOnDemand | Landing Page
Sub-task | Beem for Business | BFB-5 | Traditional market research | validation | High | 2016-01-04 16:06 | 2016-07-17 | Purchasing and analyzing market research data | jason | WebsiteOnDemand | Landing Page | 0.55
Sub-task | Beem for Business | BFB-5 | Traditional market research | validation | Medium | 2016-01-24 16:06 | 2016-07-19 | Articles and industry news about the beem4biz target market | jason | WebsiteOnDemand | Landing Page | 1
Sub-task | Beem for Business | BFB-5 | Traditional market research | validation | Medium | 2016-01-24 16:06 | 2016-09-05 | Financial analysis and revenue structure analysis of legacy industry players | jason | WebsiteOnDemand | Landing Page | 0.87
Sub-task | Beem for Business | BFB-4 | Landing page validation | validation | Medium | 2016-01-04 16:06 | 2016-09-12 | Meeting to analyze the A/B testing data and further conclusions and decide about landing page launch date | jason | WebsiteOnDemand | Landing Page | 3
Sub-task | Beem for Business | BFB-3 | Customer interviews | validation | Low | 2016-01-24 16:06 | 2016-05-15 |  | jason | WebsiteOnDemand | Validation | 21.8
Task | Beem for Business | BFB-1 | Secure and buy the domain name | web | High | 2016-01-04 16:06 | 2016-05-15 |  | jason | WebsiteOnDemand | Landing Page
|  | 54 | [9 empty] | 1231.61