## Current Workload
Project Status Report | [5 empty] | 82
Report ran (date) | 2017-05-16 09:34
Report ran (time) | 2017-05-16 09:34
Report ran by | admin
Description | This report contains a snap shot of all the currently active requests in BOT. EPICs are returned by the following filter http://jira.greatestcompany.local/issues/?filter=16001
BLANK
Key | Summary | Status | Activity Status | Due | Reporting Comments | RAG | SET Lead | Acc Man | Sales Director | Age of Issue
MPS-668 | Hydro platform upgrade | In Progress | Planning | 2016-11-11 | No additional comments. | green | Noel Lane | Davis Eggvolt | Jane Lizwood | 34w 6d 23m 26s
MPS-672 | Pebblepad TRIAL | Closed |  | 2016-12-01 | Waiting for sales to confirm completion. | green | John Tudd | Mare Higgins | Nicolde McAlister | 34w 1d 20h 36m 28s
MPS-516 | FT Backup TBAG Load | Waiting | Waiting for Sales | 2016-12-30 | Waiting for equipment return - action with Johnto confirm return dates | red | Nathan Wiggs | Jane Lizwood | Shawn Shapiro | 47w 4d 12h 5m 35s
MPS-538 | FT Trial Mode and upgrade | In Progress | Active | 2017-01-27 |  | green | Jane Lizwood |  |  | 41w 4d 8h 56m 1s
MPS-1167 | Service Reactivation for Bsystems Co. | Complete | Ready to close | 2017-03-31 | Waiting for sales to confirm completion. | green | John Tudd | Shiska Todd | Nicolde McAlister | 17w 8h 34m 51s
MPS-1323 | Request of FT Service Transfer to SSC Tothanham | Complete | Ready to close | 2017-03-31 | Waiting for sales to confirm completion. | green | John Tudd | Shiska Todd | Nicolde McAlister | 9w 5d 6h 13m 30s
MPS-1357 | Get pproval for Stathen FT Fixed Price Plan and Secure RW Sell Back to Stathen | Waiting | Waiting for Customer/Partner | 2017-04-07 | Awaiting PO from Stathan | red | Bruce Wigg | Todd McDonell | Nathan Wiggs | 7w 6d 13h 53m 18s
MPS-440 | T4 TTJ to combine PFT contracts | In Progress | Waiting for Customer/Partner | 2017-04-28 | Issue with TTK PO has been resolved. Great Co. has accepted the de-escalation rate proposed by customer. Work with Sissy will continue. | amber | Bruce Wigg | Nathan Wiggs | Nathan Wiggs | 42w 19h 36m 28s
MPS-426 | Warranty and Bronze Support Quote - TFT | Waiting | Active | 2017-04-28 | Bruce and Nathan have a meeting with the customer on 8 May to discuss the requirements so Robert will be able to price the support requirement on his return to the office on 10 May 2017. | green | John Tudd | Davis Eggvolt | Nathan Wiggs | 44w 5d 21m 29s
MPS-1401 | Nortus End of Contract Project | In Progress | Planning | 2017-04-28 |  | green | Bruce Wigg | Shiska Todd | Nathan Wiggs | 5w 3d 17h 25m 28s
MPS-1408 | Nortus VPN Establishment | Waiting | Awaiting confirmation of completion | 2017-04-28 | Waiting for confirmation that service has been set up and finalised by B Systems before closing | green | John Tudd | Shiska Todd | Nathan Wiggs | 4w 6d 24m 2s
MPS-839 | Cobra M3 Installation for Navy | In Progress |  | 2017-05-06 | Still commissioning to be completed - before 26th May Documentation will be put together this week and sent to HHF | green | Shiska Todd | Davis Eggvolt | Nathan Wiggs | 30w 6d 17h 10m 22s
MPS-428 | Removed for privacy reasons | In Progress |  | 2017-05-12 | Removed for privacy reasons | amber | Shiska Todd | Davis Eggvolt | Removed for privacy reasons | 43w 4d 20h 43m 27s
MPS-971 | Removed for privacy reasons | In Progress | Planning | 2017-05-12 | Removed for privacy reasons | green | Shiska Todd | Davis Eggvolt | Removed for privacy reasons | 27w 6d 15h 54m 27s
MPS-1161 | Removed for privacy reasons | In Progress | Active | 2017-05-26 | Removed for privacy reasons | green | John Tudd | Davis Eggvolt | Removed for privacy reasons | 17w 5d 14h 26m 28s
MPS-977 | Removed for privacy reasons | Waiting | Waiting on Central Function | 2017-05-26 | Removed for privacy reasons | green | John Tudd | Davis Eggvolt | Removed for privacy reasons | 27w 5d 12h 16m 29s
MPS-507 | Removed for privacy reasons | In Progress | Active | 2017-05-31 | Removed for privacy reasons | amber | John Tudd | Bruce Wigg | Removed for privacy reasons | 37w 5d 21h 4m 11s
MPS-1386 | Removed for privacy reasons | In Progress | Reviewing request | 2017-05-31 | Removed for privacy reasons | green | John Tudd | Removed for privacy reasons | Removed for privacy reasons | 6w 4d 19h 59m 15s
MPS-1387 | Removed for privacy reasons | In Progress | Planning | 2017-06-01 | Removed for privacy reasons | green | John Tudd | Removed for privacy reasons | Removed for privacy reasons | 6w 4d 14h 2m 28s
MPS-1416 | Removed for privacy reasons | In Progress | Reviewing request | 2017-06-07 | Removed for privacy reasons | green | John Tudd | Removed for privacy reasons | Removed for privacy reasons | 3w 5d 18h 25m 31s
MPS-1426 | Removed for privacy reasons | In Progress | Planning | 2017-06-12 | Removed for privacy reasons | red | John Tudd | Removed for privacy reasons | Removed for privacy reasons | 2w 5d 15h 32m 29s
MPS-1460 | Removed for privacy reasons | In Progress | Planning | 2017-06-26 | Removed for privacy reasons | green | John Tudd | Removed for privacy reasons | Removed for privacy reasons | 4d 19h 42m 34s
MPS-703 | Removed for privacy reasons | Waiting | Waiting for Sales | 2017-06-30 | Removed for privacy reasons | green | Bruce Wigg | Removed for privacy reasons | Removed for privacy reasons | 34w 3d 10h 31m 29s
MPS-736 | Removed for privacy reasons | In Progress | Active | 2017-06-30 | Removed for privacy reasons | green | Bruce Wigg | Removed for privacy reasons | Removed for privacy reasons | 33w 5d 10h 2m 29s
MPS-435 | Removed for privacy reasons | Waiting | Waiting for Customer/Partner | 2017-06-30 | Removed for privacy reasons | green | Bruce Wigg | Removed for privacy reasons | Removed for privacy reasons | 42w 4d 19h 57m 46s
MPS-719 | Removed for privacy reasons | Waiting | On-hold | 2017-06-30 | Removed for privacy reasons | red | Bruce Wigg | Removed for privacy reasons | Removed for privacy reasons | 34w 7h 58m 29s
MPS-1389 | Removed for privacy reasons | In Progress | Active | 2017-06-30 | Removed for privacy reasons | green | Bruce Wigg | Removed for privacy reasons | Removed for privacy reasons | 5w 6d 19h 22m 18s
MPS-1392 | Removed for privacy reasons | In Progress | Active | 2017-06-30 | Removed for privacy reasons | green | Bruce Wigg | Removed for privacy reasons | Removed for privacy reasons | 5w 6d 17h 51m 20s
MPS-1394 | Removed for privacy reasons | In Progress | Reviewing request | 2017-06-30 | Removed for privacy reasons | green | Bruce Wigg | Removed for privacy reasons | Removed for privacy reasons | 5w 5d 23h 34m 11s
MPS-1434 | Removed for privacy reasons | In Progress | Planning | 2017-07-28 | Removed for privacy reasons | green | Bruce Wigg | Removed for privacy reasons | Removed for privacy reasons | 2w 4d 14h 41m 32s
MPS-27 | Removed for privacy reasons | In Progress | Active | 2017-07-31 | Removed for privacy reasons | amber | Bruce Wigg | Removed for privacy reasons | Removed for privacy reasons | 63w 5d 43m 30s
MPS-338 | Removed for privacy reasons | In Progress | Active | 2017-07-31 | Removed for privacy reasons | amber | Bruce Wigg | Removed for privacy reasons | Removed for privacy reasons | 54w 5d 18h 10m 55s
MPS-1340 | Removed for privacy reasons | Blocked |  | 2017-07-31 | Removed for privacy reasons | red | Bruce Wigg | Removed for privacy reasons | Removed for privacy reasons | 9w 21h 46m 20s
MPS-502 | Removed for privacy reasons | Waiting | Waiting on Central Function | 2017-08-30 | Removed for privacy reasons | green | Bruce Wigg | Removed for privacy reasons | Removed for privacy reasons | 39w 5d 39m 5s
MPS-620 | Removed for privacy reasons | Waiting | On-hold | 2017-08-31 | Removed for privacy reasons | amber | Bruce Wigg | Removed for privacy reasons | Removed for privacy reasons | 35w 5d 23h 57m 30s
MPS-26 | Removed for privacy reasons | Waiting | On-hold | 2017-12-30 | Removed for privacy reasons | green | Jane Lizwood | Removed for privacy reasons | Removed for privacy reasons | 63w 5d 44m 25s
MPS-570 | Removed for privacy reasons | Waiting | Active |  | Removed for privacy reasons | green | Jane Lizwood | Removed for privacy reasons | Removed for privacy reasons | 40w 8h 35m 6s
MPS-511 | Removed for privacy reasons | In Progress | Active |  | Removed for privacy reasons | green | Jane Lizwood | Removed for privacy reasons | Removed for privacy reasons | 40w 8h 35m 7s
MPS-1179 | Removed for privacy reasons | Waiting | Waiting for Sales |  | Removed for privacy reasons | green | Jane Lizwood | Removed for privacy reasons | Removed for privacy reasons | 16w 5d 7h 58m 29s
MPS-728 | Removed for privacy reasons | In Progress | Active |  | Removed for privacy reasons | red | Jane Lizwood | Removed for privacy reasons | Removed for privacy reasons | 33w 5d 21h 31m 11s
MPS-445 | Removed for privacy reasons | To Do |  |  | Removed for privacy reasons | green | Jane Lizwood | Removed for privacy reasons | Removed for privacy reasons | 41w 4d 18h 45m 47s
MPS-565 | Removed for privacy reasons | Waiting | Executing |  | Removed for privacy reasons | green | Jane Lizwood | Removed for privacy reasons | Removed for privacy reasons | 36w 4d 23h 59m 1s
MPS-645 | Removed for privacy reasons | Waiting | Waiting for Customer/Partner |  | Removed for privacy reasons | amber | Jane Lizwood | Removed for privacy reasons | Removed for privacy reasons | 35w 4d 10h 47m 3s
MPS-1107 | Removed for privacy reasons | Waiting | On-hold |  | Removed for privacy reasons | green | Jane Lizwood | Removed for privacy reasons | Removed for privacy reasons | 21w 6d 3h 22m 27s
MPS-1108 | Removed for privacy reasons | In Progress | Planning |  | Removed for privacy reasons | green | Jane Lizwood | Removed for privacy reasons | Removed for privacy reasons | 21w 5d 23h 30m 29s
MPS-1177 | Removed for privacy reasons | In Progress | Planning |  | Removed for privacy reasons | green | Jane Lizwood | Removed for privacy reasons | Removed for privacy reasons | 16w 5d 9h 26m 6s
MPS-1246 | Removed for privacy reasons | In Progress |  |  | Removed for privacy reasons | green | Jane Lizwood | Removed for privacy reasons | Removed for privacy reasons | 13w 4d 15h 2m 29s
MPS-1361 | Removed for privacy reasons | To Do |  |  | Removed for privacy reasons | green | Jane Lizwood | Removed for privacy reasons | Removed for privacy reasons | 7w 5d 12h 16m 29s
MPS-1364 | Removed for privacy reasons | In Progress | Planning |  | Removed for privacy reasons | green | Jane Lizwood | Removed for privacy reasons | Removed for privacy reasons | 7w 4d 13h 10m 29s
MPS-1373 | Removed for privacy reasons | Complete | Ready to close |  | Removed for privacy reasons | green | Jane Lizwood | Removed for privacy reasons | Removed for privacy reasons | 6w 6d 21h 32m 2s
MPS-1375 | Removed for privacy reasons | To Do |  |  | Removed for privacy reasons | green | Jane Lizwood | Removed for privacy reasons | Removed for privacy reasons | 6w 6d 20h 29s
MPS-1384 | Removed for privacy reasons | In Progress | Planning |  | Removed for privacy reasons | green | Jane Lizwood | Removed for privacy reasons | Removed for privacy reasons | 6w 5d 4h 4m 29s
MPS-1388 | Removed for privacy reasons | In Progress | Planning |  | Removed for privacy reasons | green | Jane Lizwood | Removed for privacy reasons | Removed for privacy reasons | 6w 10h 4m 28s
MPS-1402 | Removed for privacy reasons | In Progress | Planning |  | Removed for privacy reasons | green | Jane Lizwood | Removed for privacy reasons | Removed for privacy reasons | 5w 3d 6h 10m 27s
MPS-1417 | Removed for privacy reasons | On Hold | Waiting for Customer/Partner |  | Removed for privacy reasons | red | Jane Lizwood | Removed for privacy reasons | Removed for privacy reasons | 3w 5d 18h 29s
MPS-1421 | Removed for privacy reasons | To Do |  |  | Removed for privacy reasons | green | Jane Lizwood | Removed for privacy reasons | Removed for privacy reasons | 3w 3d 16h 52m 29s
MPS-1428 | Removed for privacy reasons | To Do |  |  | Removed for privacy reasons | green | Jane Lizwood | Removed for privacy reasons | Removed for privacy reasons | 2w 5d 55m 4s
MPS-1429 | Removed for privacy reasons | To Do |  |  | Removed for privacy reasons | green | Jane Lizwood | Removed for privacy reasons | Removed for privacy reasons | 2w 5d 43m 4s
MPS-1430 | Removed for privacy reasons | To Do |  |  | Removed for privacy reasons | green | Jane Lizwood | Removed for privacy reasons | Removed for privacy reasons | 2w 5d 32m 17s
MPS-1438 | Removed for privacy reasons | In Progress | Planning |  | Removed for privacy reasons | green | Jane Lizwood | Removed for privacy reasons | Removed for privacy reasons | 1w 6d 15h 18m 29s
MPS-1439 | Removed for privacy reasons | To Do |  |  | Removed for privacy reasons | green | Jane Lizwood | Removed for privacy reasons | Removed for privacy reasons | 1w 6d 1h 28m 28s
MPS-1440 | Removed for privacy reasons | Closed |  |  | Removed for privacy reasons | green | Jane Lizwood | Removed for privacy reasons | Removed for privacy reasons | 1w 14h 38m 49s
MPS-1450 | Removed for privacy reasons | Closed |  |  | Removed for privacy reasons | green | Jane Lizwood | Removed for privacy reasons | Removed for privacy reasons | 5d 22h 11m 45s
MPS-1451 | Removed for privacy reasons | In Progress | Planning |  | Removed for privacy reasons | green | Jane Lizwood | Removed for privacy reasons | Removed for privacy reasons | 1w 3d 11h 12m 29s
MPS-1454 | Removed for privacy reasons | Closed | Waiting for triage |  | Removed for privacy reasons | green | Removed for privacy reasons | Removed for privacy reasons | Removed for privacy reasons | 20h 52m 42s
MPS-1455 | Removed for privacy reasons | In Progress | Planning |  | Removed for privacy reasons | green | Removed for privacy reasons | Removed for privacy reasons | Removed for privacy reasons | 1w 15h 22m 29s
MPS-1456 | Removed for privacy reasons | In Progress | Planning |  | Removed for privacy reasons | green | Removed for privacy reasons | Removed for privacy reasons | Removed for privacy reasons | 1w 13h 8m 29s
MPS-1458 | Removed for privacy reasons | In Progress | Planning |  | Removed for privacy reasons | green | Removed for privacy reasons | Removed for privacy reasons | Removed for privacy reasons | 6d 10h 44m 29s
MPS-1459 | Removed for privacy reasons | In Progress | Planning |  | Removed for privacy reasons | green | Removed for privacy reasons | Removed for privacy reasons | Removed for privacy reasons | 5d 9h 8m 29s
MPS-1462 | Removed for privacy reasons | In Progress | Planning |  | Removed for privacy reasons | green | Removed for privacy reasons | Removed for privacy reasons | Removed for privacy reasons | 4d 3h 24m 28s
MPS-1464 | Removed for privacy reasons | Logged | Waiting for triage |  | Removed for privacy reasons | green | Removed for privacy reasons | Removed for privacy reasons | Removed for privacy reasons | 3d 2h 2m 29s
MPS-1465 | Removed for privacy reasons | Logged | Waiting for triage |  | Removed for privacy reasons | green | Removed for privacy reasons | Removed for privacy reasons | Removed for privacy reasons | 15h 50m 29s
MPS-1466 | Removed for privacy reasons | Logged | Waiting for triage |  | Removed for privacy reasons | green | Removed for privacy reasons | Removed for privacy reasons | Removed for privacy reasons | 15h 50m 26s
MPS-1467 | Removed for privacy reasons | Logged | Waiting for triage |  | Removed for privacy reasons | green | Removed for privacy reasons | Removed for privacy reasons | Removed for privacy reasons | 10h 38m 28s

## Planner
Planner (6 month forcast)
Report ran (date) |  |  | 2017-05-16 09:34
Report ran (time) |  |  | 2017-05-16 09:34
Report ran by |  |  | admin
Description |  |  | This report contains all the currently active EPICs. EPICs are returned by the following filter http://jira.greatcomoany.local/issues/?filter=16001
Plan Start | 2017-11-16 | [6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Base Date | 2017-11-13
[8 empty] | Week-3 | Week-2 | Week-1 | Week0 | Week1 | Week2 | Week3 | Week4 | Week5 | Week6 | Week7 | Week8 | Week9 | Week10 | Week11 | Week12 | Week13 | Week14 | Week15 | Week16 | Week17 | Week18 | Week19 | Week20 | Week21 | Week22 | Week23 | Week24 | Week25 | Week26 | END
Key | Summary | Status | Assignee | P/A | Start | End | Due | 2017-10-16 | 2017-10-23 | 2017-10-30 | 2017-11-06 | 2017-11-13 | 2017-11-20 | 2017-11-27 | 2017-12-04 | 2017-12-11 | 2017-12-18 | 2017-12-25 | 2018-01-01 | 2018-01-08 | 2018-01-15 | 2018-01-22 | 2018-01-29 | 2018-02-05 | 2018-02-12 | 2018-02-19 | 2018-02-26 | 2018-03-05 | 2018-03-12 | 2018-03-19 | 2018-03-26 | 2018-04-02 | 2018-04-09 | 2018-04-16 | 2018-04-23 | 2018-04-30 | 2018-05-07 | 2018-05-14
MPS-668 | Hydro platform upgrade | In Progress | Jane Lizwood | Planned |  |  | 2016-09-30
|  |  |  | Actual | 2016-11-04 | 2017-04-30 | 2016-11-11
MPS-672 | Pebblepad TRIAL | Closed | Bruce Wigg | Planned |  |  | 2016-09-30
|  |  |  | Actual | 2017-04-05 | 2017-05-12 | 2016-12-01
MPS-516 | FT Backup TBAG Load | Waiting | Jane Lizwood | Planned
|  |  |  | Actual | 2016-07-01 | 2016-10-12 | 2016-12-30
MPS-538 | FT Trial Mode and upgrade | In Progress | Bruce Wigg | Planned
|  |  |  | Actual | 2016-09-01 |  | 2017-01-27 | bar: 1 to 30
MPS-1167 | Service Reactivation for Bsystems Co. | Complete | Davis Eggvolt | Planned |  |  | 2017-01-20
|  |  |  | Actual | 2017-01-25 | 2017-05-13 15:05 | 2017-03-31
MPS-1323 | Request of FT Service Transfer to SSC Tothanham | Complete | Davis Eggvolt | Planned |  |  | 2017-03-31
|  |  |  | Actual | 2017-03-08 | 2017-05-13 15:04 | 2017-03-31
MPS-1357 | Get Approval for Stathen FT Fixed Price Plan and Secure RW Sell Back to Stathen | Waiting | Bruce Wigg | Planned
|  |  |  | Actual | 2017-03-24 | 2017-04-07 | 2017-04-07
MPS-440 | T4 TTJ to combine PFT contracts | In Progress | Bruce Wigg | Planned |  |  | 2016-09-30
|  |  |  | Actual | 2016-05-02 | 2016-09-30 | 2017-04-28
MPS-426 | T4 TTJ to combine LPL contracts | Waiting | Davis Eggvolt | Planned |  |  | 2016-09-30
|  |  |  | Actual | 2016-07-07 | 2016-09-30 | 2017-04-28
MPS-1401 | Warranty and Bronze Support Quote - TFT | In Progress | Bruce Wigg | Planned
|  |  |  | Actual | 2017-05-15 13:57 |  | 2017-04-28 | bar: 1 to 30
MPS-1408 | Nortus End of Contract Project | Waiting | Bruce Wigg | Planned |  |  | 2017-04-13
|  |  |  | Actual | 2017-04-12 |  | 2017-04-28 | bar: 1 to 30
MPS-839 | Nortus VPN Establishment | In Progress | Davis Eggvolt | Planned |  |  | 2017-03-31
|  |  |  | Actual | 2016-10-19 |  | 2017-05-06 | bar: 1 to 30
MPS-428 | Removed for privacy reasons | In Progress | Removed for privacy reasons | Planned |  |  | 2017-05-19
|  |  |  | Actual | 2016-07-20 |  | 2017-05-12 | bar: 1 to 30
MPS-971 | Removed for privacy reasons | In Progress | Removed for privacy reasons | Planned |  |  | 2016-11-07
|  |  |  | Actual | 2017-05-13 | 2017-02-23 | 2017-05-12
MPS-1161 | Removed for privacy reasons | In Progress | Removed for privacy reasons | Planned |  |  | 2017-05-26
|  |  |  | Actual | 2017-01-18 |  | 2017-05-26 | bar: 1 to 30
MPS-977 | Removed for privacy reasons | Waiting | Removed for privacy reasons | Planned |  |  | 2016-11-02
|  |  |  | Actual | 2016-11-09 | 2016-11-23 | 2017-05-26
MPS-507 | Removed for privacy reasons | In Progress | Removed for privacy reasons | Planned |  |  | 2016-08-31
|  |  |  | Actual | 2016-08-22 | 2017-05-01 | 2017-05-31
MPS-1386 | Removed for privacy reasons | In Progress | Removed for privacy reasons | Planned |  |  | 2017-05-31
|  |  |  | Actual | 2017-03-30 |  | 2017-05-31 | bar: 1 to 30
MPS-1387 | Removed for privacy reasons | In Progress | Removed for privacy reasons | Planned |  |  | 2017-06-01
|  |  |  | Actual | 2017-04-10 |  | 2017-06-01 | bar: 1 to 30
MPS-1416 | Removed for privacy reasons | In Progress | Removed for privacy reasons | Planned |  |  | 2017-06-07
|  |  |  | Actual |  |  | 2017-06-07
MPS-1426 | Removed for privacy reasons | In Progress | Removed for privacy reasons | Planned |  |  | 2017-04-28
|  |  |  | Actual | 2017-05-02 |  | 2017-06-12 | bar: 1 to 30
MPS-1460 | Removed for privacy reasons | In Progress | Removed for privacy reasons | Planned | 2017-05-15 00:00:00.0 | 2017-05-31 00:00:00.0 | 2017-06-26
|  |  |  | Actual | 2017-05-15 17:41 |  | 2017-06-26 | bar: 1 to 30
MPS-703 | Removed for privacy reasons | Waiting | Removed for privacy reasons | Planned |  |  | 2017-06-30
|  |  |  | Actual | 2016-10-17 |  | 2017-06-30 | bar: 1 to 30
MPS-736 | Removed for privacy reasons | In Progress | Removed for privacy reasons | Planned
|  |  |  | Actual | 2016-12-07 |  | 2017-06-30 | bar: 1 to 30
MPS-435 | Removed for privacy reasons | Waiting | Removed for privacy reasons | Planned
|  |  |  | Actual | 2016-08-01 | 2016-11-14 | 2017-06-30
MPS-719 | Removed for privacy reasons | Waiting | Removed for privacy reasons | Planned |  |  | 2016-10-21
|  |  |  | Actual |  |  | 2017-06-30
MPS-1389 | Removed for privacy reasons | In Progress | Removed for privacy reasons | Planned |  |  | 2017-06-30
|  |  |  | Actual | 2017-04-01 |  | 2017-06-30 | bar: 1 to 30
MPS-1392 | Removed for privacy reasons | In Progress | Removed for privacy reasons | Planned |  |  | 2017-06-30
|  |  |  | Actual | 2017-04-01 |  | 2017-06-30 | bar: 1 to 30
MPS-1394 | Removed for privacy reasons | In Progress | Removed for privacy reasons | Planned |  |  | 2017-03-31
|  |  |  | Actual | 2017-01-01 | 2017-03-31 | 2017-06-30
MPS-1434 | Removed for privacy reasons | In Progress | Removed for privacy reasons | Planned
|  |  |  | Actual | 2017-04-27 19:20 |  | 2017-07-28 | bar: 1 to 30
MPS-27 | Removed for privacy reasons | In Progress | Removed for privacy reasons | Planned |  |  | 2016-12-30
|  |  |  | Actual | 2016-02-04 | 2016-08-31 | 2017-07-31
MPS-338 | Removed for privacy reasons | In Progress | Removed for privacy reasons | Planned
|  |  |  | Actual | 2016-03-29 | 2016-06-01 | 2017-07-31
MPS-1340 | Removed for privacy reasons | Blocked | Removed for privacy reasons | Planned |  |  | 2017-07-31
|  |  |  | Actual | 2017-03-15 |  | 2017-07-31 | bar: 1 to 30
MPS-502 | Removed for privacy reasons | Waiting | Removed for privacy reasons | Planned |  |  | 2017-08-30
|  |  |  | Actual | 2016-11-09 | 2017-09-29 | 2017-08-30
MPS-620 | Removed for privacy reasons | Waiting | Removed for privacy reasons | Planned |  |  | 2016-09-27
|  |  |  | Actual | 2016-10-07 | 2016-10-11 | 2017-08-31
MPS-26 | Removed for privacy reasons | Waiting | Removed for privacy reasons | Planned |  |  | 2016-07-29
|  |  |  | Actual | 2016-05-10 | 2016-10-18 | 2017-12-30 | bar: 11
MPS-570 | Removed for privacy reasons | Waiting | Removed for privacy reasons | Planned
|  |  |  | Actual | 2016-09-07 | 2016-09-26
MPS-511 | Removed for privacy reasons | In Progress | Removed for privacy reasons | Planned
|  |  |  | Actual | 2016-09-06 | 2016-09-26
MPS-1179 | Removed for privacy reasons | Waiting | Removed for privacy reasons | Planned |  |  | 2017-02-28
Actual
MPS-728 | Removed for privacy reasons | In Progress | Removed for privacy reasons | Planned |  |  | 2017-04-30
|  |  |  | Actual | 2016-09-21 | 2017-11-01 | bar: 1 to 3
MPS-445 | Removed for privacy reasons | To Do | Removed for privacy reasons | Planned |  |  | 2017-02-28
Actual
MPS-565 | Removed for privacy reasons | Waiting | Removed for privacy reasons | Planned |  |  | 2017-01-02
|  |  |  | Actual | 2016-11-02 | 2016-11-02
MPS-645 | Removed for privacy reasons | Waiting | Removed for privacy reasons | Planned
|  |  |  | Actual | 2016-09-01 | 2017-02-24
MPS-1107 | Removed for privacy reasons | Waiting | Removed for privacy reasons | Planned
|  |  |  | Actual | 2017-03-28 | bar: 1 to 30
MPS-1108 | Removed for privacy reasons | In Progress | Removed for privacy reasons | Planned
|  |  |  | Actual | 2017-03-02 | bar: 1 to 30
MPS-1177 | Removed for privacy reasons | In Progress | Removed for privacy reasons | Planned
|  |  |  | Actual | 2017-03-14 | bar: 1 to 30
MPS-1246 | Removed for privacy reasons | In Progress | Removed for privacy reasons | Planned |  |  | 2017-06-16
|  |  |  | Actual | 2017-02-18 | bar: 1 to 30
MPS-1361 | Removed for privacy reasons | To Do | Removed for privacy reasons | Planned |  |  | 2017-04-09
Actual
MPS-1364 | Removed for privacy reasons | In Progress | Removed for privacy reasons | Planned |  |  | 2017-04-05
|  |  |  | Actual | 2017-05-04 | 2017-05-03
MPS-1373 | Removed for privacy reasons | Complete | Removed for privacy reasons | Planned |  |  | 2018-03-31 | bar: 24
|  |  |  | Actual | 2017-05-15 18:30 | 2017-05-15 18:31
MPS-1375 | Removed for privacy reasons | To Do | Removed for privacy reasons | Planned |  |  | 2017-06-30
Actual
MPS-1384 | Removed for privacy reasons | In Progress | Removed for privacy reasons | Planned |  |  | 2017-04-30
|  |  |  | Actual | 2017-05-02 | bar: 1 to 30
MPS-1388 | Removed for privacy reasons | In Progress | Removed for privacy reasons | Planned |  |  | 2017-05-19
|  |  |  | Actual | 2017-04-07 | bar: 1 to 30
MPS-1402 | Removed for privacy reasons | In Progress | Removed for privacy reasons | Planned
|  |  |  | Actual | 2017-04-13 | bar: 1 to 30
MPS-1417 | Removed for privacy reasons | On Hold | Removed for privacy reasons | Planned |  |  | 2017-05-04
Actual
MPS-1421 | Removed for privacy reasons | To Do | Removed for privacy reasons | Planned
Actual
MPS-1428 | Removed for privacy reasons | To Do | Removed for privacy reasons | Planned |  |  | 2017-05-12
Actual
MPS-1429 | Removed for privacy reasons | To Do | Removed for privacy reasons | Planned
|  |  |  | Actual |  | 2017-07-03
MPS-1430 | Removed for privacy reasons | To Do | Removed for privacy reasons | Planned
Actual
MPS-1438 | Removed for privacy reasons | In Progress | Removed for privacy reasons | Planned |  |  | 2017-05-22
|  |  |  | Actual | 2017-05-05 | bar: 1 to 30
MPS-1439 | Removed for privacy reasons | To Do | Removed for privacy reasons | Planned |  |  | 2017-05-24
Actual
MPS-1440 | Removed for privacy reasons | Closed | Removed for privacy reasons | Planned
|  |  |  | Actual | 2017-05-11 | 2017-05-11
MPS-1450 | Removed for privacy reasons | Closed | Removed for privacy reasons | Planned |  |  | 2017-05-05
|  |  |  | Actual | 2017-05-05 | 2017-05-11
MPS-1451 | Removed for privacy reasons | In Progress | Removed for privacy reasons | Planned |  |  | 2017-07-03
|  |  |  | Actual | 2017-05-11 | bar: 1 to 30
MPS-1454 | Removed for privacy reasons | Closed | Removed for privacy reasons | Planned
Actual
MPS-1455 | Removed for privacy reasons | In Progress | Removed for privacy reasons | Planned |  |  | 2017-05-26
|  |  |  | Actual | 2017-05-10 20:40 | bar: 1 to 30
MPS-1456 | Removed for privacy reasons | In Progress | Removed for privacy reasons | Planned |  |  | 2017-10-27 | bar: 2
|  |  |  | Actual | 2017-05-09 16:33 | bar: 1 to 30
MPS-1458 | Removed for privacy reasons | In Progress | Removed for privacy reasons | Planned |  |  | 2017-05-22
|  |  |  | Actual | 2017-05-10 | bar: 1 to 30
MPS-1459 | Removed for privacy reasons | In Progress | Removed for privacy reasons | Planned |  |  | 2017-05-31
|  |  |  | Actual | 2017-05-11 19:27 | bar: 1 to 30
MPS-1462 | Removed for privacy reasons | In Progress | Removed for privacy reasons | Planned |  |  | 2017-06-14
|  |  |  | Actual | 2017-05-13 01:48 | bar: 1 to 30
MPS-1464 | Removed for privacy reasons | Logged | Removed for privacy reasons | Planned
Actual
MPS-1465 | Removed for privacy reasons | Logged | Removed for privacy reasons | Planned |  |  | 2017-05-31
Actual
MPS-1466 | Removed for privacy reasons | Logged | Removed for privacy reasons | Planned |  |  | 2017-05-31
Actual
MPS-1467 | Removed for privacy reasons | Logged | Removed for privacy reasons | Planned
Actual

## Volume Measures
Status | (All)
Row Labels | # Epics
Bruce Wigg | 16
Noel Lane | 1
John Tudd | 13
Nathan Wiggs | 1
Jane Lizwood | 30
Shiska Todd | 3
Removed for privacy reasons | 10
Grand Total | 74