## Projects
| SSPI |  | INT |  | Total Sum of Time Estimate | Total Sum of Time Spent
| Sum of Time Estimate | Sum of Time Spent | Sum of Time Estimate | Sum of Time Spent
BackEnd Team
Done | 518 | 212 | 150 | 151 | 668 | 363
In Progress | 320 | 152 | 230 | 151 | 550 | 303
To Do | 481 | 193 | 94 | 48 | 575 | 241
CloudDev Team
Done | 180 | 231 | 150 | 96 | 330 | 327
In Progress | 345 | 189 | 192 | 126 | 537 | 315
To Do | 80 | 159 | 197 | 124 | 277 | 283
Grand Total | 1924 | 1136 | 1013 | 696 | 2937 | 1832

## Assignees
| INT |  | SSPI |  | Total Sum of Time Estimate | Total Sum of Time Spent
| Sum of Time Estimate | Sum of Time Spent | Sum of Time Estimate | Sum of Time Spent
Bob Mitchell | 80 | 38 | 200 | 312 | 280 | 350
Casey Ford | 373 | 282 | 308 | 220 | 681 | 502
Dalia Lens | 90 | 75 | 220 | 86 | 310 | 161
Levente Szabo | 110 | 45 | 100 | 66 | 210 | 111
Liam Farrell | 120 | 36 |  |  | 120 | 36
Owen Klyed |  |  | 401 | 127 | 401 | 127
Robert Mongose | 120 | 130 | 345 | 189 | 465 | 319
Zoe Barnes | 120 | 90 | 350 | 136 | 470 | 226
Grand Total | 1013 | 696 | 1924 | 1136 | 2937 | 1832

## Accounts
| INT |  | SSPI |  | Total Sum of Time Estimate | Total Sum of Time Spent
| Sum of Time Estimate | Sum of Time Spent | Sum of Time Estimate | Sum of Time Spent
Grid OnDemand (GRIDOD) |  |  | 708 | 502 | 708 | 502
Smart Metering (SMARTMETER) |  |  | 729 | 396 | 729 | 396
MobileApp Dev (APPDev) | 393 | 310 |  |  | 393 | 310
Utility Reporting (UTILITYREP) | 67 | 40 | 487 | 238 | 554 | 278
CloudMaint (CLOUDMAINT) | 383 | 196 |  |  | 383 | 196
WebsiteOnDemand (WEB) | 170 | 150 |  |  | 170 | 150
Grand Total | 1013 | 696 | 1924 | 1136 | 2937 | 1832

## Iterations
Sum of Time Spent
| 1 | 2 | 3 | Grand Total
SSPI | 667 | 285 | 184 | 1136
INT | 194 | 116 | 386 | 696
Grand Total | 861 | 401 | 570 | 1832

## Teams
| INT |  | SSPI |  | Total Sum of Time Estimate | Total Sum of Time Spent
| Sum of Time Estimate | Sum of Time Spent | Sum of Time Estimate | Sum of Time Spent
BackEnd Team | 474 | 350 | 1319 | 557 | 1793 | 907
CloudDev Team | 539 | 346 | 605 | 579 | 1144 | 925
Grand Total | 1013 | 696 | 1924 | 1136 | 2937 | 1832

## Issues
Key | Project Key | Issue Type | Priority | Status | Assignee | Component/s | Version/s | Account | Iteration | Team | Time Estimate | Time Spent
SSPI-20 | SSPI | Bug | Medium | To Do | Bob Mitchell |  |  | Grid OnDemand (GRIDOD) | 2 | CloudDev Team | 20 | 40
SSPI-19 | SSPI | Task | Medium | To Do | Bob Mitchell |  |  | Grid OnDemand (GRIDOD) | 2 | CloudDev Team | 40 | 34
SSPI-18 | SSPI | Task | Medium | To Do | Owen Klyed |  |  | Utility Reporting (UTILITYREP) | 2 | BackEnd Team | 32 | 3
SSPI-17 | SSPI | Task | Medium | To Do | Owen Klyed |  |  | Grid OnDemand (GRIDOD) | 1 | BackEnd Team | 70 | 45
SSPI-16 | SSPI | Task | Medium | To Do | Owen Klyed |  |  | Smart Metering (SMARTMETER) | 1 | BackEnd Team | 129 | 56
SSPI-15 | SSPI | Task | Medium | To Do | Zoe Barnes |  |  | Utility Reporting (UTILITYREP) | 1 | BackEnd Team | 250 | 89
SSPI-14 | SSPI | Task | Medium | Done | Casey Ford |  |  | Grid OnDemand (GRIDOD) | 1 | BackEnd Team | 108 | 90
SSPI-13 | SSPI | Task | Medium | In Progress | Dalia Lens |  |  | Grid OnDemand (GRIDOD) | 1 | BackEnd Team | 120 | 30
SSPI-12 | SSPI | Task | Medium | In Progress | Dalia Lens |  |  | Grid OnDemand (GRIDOD) | 1 | BackEnd Team | 100 | 56
SSPI-11 | SSPI | Task | Medium | In Progress | Levente Szabo |  |  | Smart Metering (SMARTMETER) | 1 | BackEnd Team | 100 | 66
SSPI-10 | SSPI | Bug | Medium | In Progress | Robert Mongose |  |  | Smart Metering (SMARTMETER) | 1 | CloudDev Team | 100 | 66
SSPI-9 | SSPI | Bug | Medium | In Progress | Robert Mongose |  |  | Smart Metering (SMARTMETER) | 2 | CloudDev Team | 200 | 78
SSPI-8 | SSPI | Bug | Medium | In Progress | Robert Mongose |  |  | Utility Reporting (UTILITYREP) | 2 | CloudDev Team | 45 | 45
SSPI-7 | SSPI | Task | Medium | Done | Casey Ford |  |  | Smart Metering (SMARTMETER) | 1 | BackEnd Team | 180 | 45
SSPI-6 | SSPI | Epic | Medium | Done | Owen Klyed |  |  | Grid OnDemand (GRIDOD) | 1 | BackEnd Team | 170 | 23
SSPI-5 | SSPI | Task | Medium | Done | Zoe Barnes |  |  | Utility Reporting (UTILITYREP) | 1 | CloudDev Team | 100 | 47
SSPI-4 | SSPI | Task | Medium | To Do | Casey Ford |  |  | Smart Metering (SMARTMETER) | 2 | CloudDev Team | 20 | 85
SSPI-3 | SSPI | Task | Medium | Done | Bob Mitchell |  |  | Grid OnDemand (GRIDOD) | 3 | CloudDev Team | 20 | 97
SSPI-2 | SSPI | Task | Medium | Done | Bob Mitchell |  |  | Grid OnDemand (GRIDOD) | 3 | CloudDev Team | 60 | 87
SSPI-1 | SSPI | Task | Medium | Done | Bob Mitchell |  |  | Utility Reporting (UTILITYREP) | 1 | BackEnd Team | 60 | 54
INT-21 | INT | Task | Medium | In Progress | Robert Mongose |  |  | CloudMaint (CLOUDMAINT) | 3 | BackEnd Team | 90 | 47
INT-20 | INT | Bug | Medium | In Progress | Robert Mongose |  |  | MobileApp Dev (APPDev) | 3 | BackEnd Team | 0 | 43
INT-19 | INT | Bug | Medium | In Progress | Liam Farrell |  |  | WebsiteOnDemand (WEB) | 2 | CloudDev Team | 80 | 23
INT-18 | INT | Bug | Medium | In Progress | Liam Farrell |  |  | CloudMaint (CLOUDMAINT) | 2 | BackEnd Team | 40 | 13
INT-17 | INT | Bug | Medium | In Progress | Bob Mitchell |  |  | CloudMaint (CLOUDMAINT) | 2 | BackEnd Team | 80 | 6
INT-16 | INT | Bug | Medium | In Progress | Bob Mitchell |  |  | MobileApp Dev (APPDev) | 2 | CloudDev Team | 0 | 32
INT-15 | INT | Bug | Medium | In Progress | Zoe Barnes |  |  | WebsiteOnDemand (WEB) | 2 | BackEnd Team | 20 | 42
INT-14 | INT | Bug | Medium | In Progress | Zoe Barnes |  |  | CloudMaint (CLOUDMAINT) | 3 | CloudDev Team | 80 | 24
INT-13 | INT | Epic | Medium | In Progress | Zoe Barnes |  |  | MobileApp Dev (APPDev) | 3 | CloudDev Team | 20 | 24
INT-12 | INT | Epic | Medium | In Progress | Casey Ford |  |  | CloudMaint (CLOUDMAINT) | 3 | CloudDev Team | 12 | 23
INT-11 | INT | Epic | Medium | Done | Casey Ford |  |  | MobileApp Dev (APPDev) | 3 | BackEnd Team | 20 | 53
INT-10 | INT | Epic | Medium | Done | Dalia Lens |  |  | MobileApp Dev (APPDev) | 1 | BackEnd Team | 90 | 75
INT-9 | INT | Task | Medium | Done | Casey Ford |  |  | WebsiteOnDemand (WEB) | 1 | CloudDev Team | 30 | 62
INT-8 | INT | Task | Medium | Done | Casey Ford |  |  | WebsiteOnDemand (WEB) | 1 | BackEnd Team | 40 | 23
INT-7 | INT | Task | Medium | Done | Casey Ford |  |  | MobileApp Dev (APPDev) | 1 | CloudDev Team | 120 | 34
INT-6 | INT | Task | Medium | To Do | Casey Ford |  |  | CloudMaint (CLOUDMAINT) | 3 | BackEnd Team | 51 | 43
INT-5 | INT | Task | Medium | To Do | Casey Ford |  |  | MobileApp Dev (APPDev) | 3 | CloudDev Team | 70 | 4
INT-4 | INT | Task | Medium | To Do | Levente Szabo |  |  | Utility Reporting (UTILITYREP) | 3 | CloudDev Team | 67 | 40
INT-3 | INT | Task | Medium | To Do | Casey Ford |  |  | CloudMaint (CLOUDMAINT) | 3 | CloudDev Team | 30 | 40
INT-2 | INT | Task | Low | To Do | Levente Szabo |  |  | MobileApp Dev (APPDev) | 3 | BackEnd Team | 43 | 5
INT-1 | INT | Task | High | To Do | Robert Mongose |  |  | MobileApp Dev (APPDev) | 3 | CloudDev Team | 30 | 40