## Resource Utilization
Row Labels | Sum of Original story points
Jan | 14
Sensors Team | 14
Feb | 7
FitBand Team | 7
Mar | 41
Sensors Team | 41
Apr | 67
FitBand Team | 48
Sensors Team | 19
May | 30
Sensors Team | 16
FitBand Team | 14
Jun | 103
FitBand Team | 91
Sensors Team | 12
Jul | 250
FitBand Team | 243
Analytics Team | 7
Aug | 56
FitBand Team | 56
Sep | 44
FitBand Team | 24
Analytics Team | 20
Oct | 194
FitBand Team | 98
Analytics Team | 57
Sensors Team | 39
Nov | 105
Analytics Team | 98
FitBand Team | 7
Grand Total | 911

## Resource Cost
Row Labels | Sum of Cost
FitBand Team | 3613
Data transmission | 1360
Data collection | 926
Smart door integration | 522
Smart appliances integration | 430
Charger | 277
Battery | 75
Touch sensors | 23
Sensors Team | 2306
Environmental sensors | 912
Body presence sensor | 775
Touch sensors | 342
Movement sensors | 277
Analytics Team | 1791
Metrics calculation | 1768
Data transmission | 23
Grand Total | 7710

## Status Report
Row Labels | Sum of Logged hours | Sum of Original estimate
Initiative | 93 | 469
Sharing training data | 1 | 26
Smart home integrations | 2 | 35
Power sources | 6 | 54
Next generation smart sensors | 28 | 137
Tracking training data | 56 | 217
Grand Total | 93 | 469

## Issue Navigator
T | Key | Summary | Status | Parent Link | Epic Link | Target start | Target end | Year | Month | Day | Team | Original story points | Cost | Original estimate | Logged hours | Initiative progress
Initiative | RUBBERBALL-14 | Power sources | Under development |  |  | 2019-04-06 02:00 | 2019-07-16 02:00 | 2019 | Jul | 16 | FitBand Team | 70 | 352 | 54 | 6 | 11.11%
Epic | RUBBERBALL-16 | Battery | Under development | RUBBERBALL-14 Power sources |  | 2019-04-10 02:00 | 2019-07-08 02:00 | 2019 | Jul | 8 | FitBand Team | 10 | 75 | 9 | 1
Task | RUBBERBALL-19 | Call the Power API to gather information about device battery | Under development |  | Battery | 2019-04-16 02:00 | 2019-07-07 02:00 | 2019 | Jul | 7 | FitBand Team | 4 | 43 | 4 | 0
Task | RUBBERBALL-18 | Use the Battery object to represents the properties of a device's battery | To Do |  | Battery | 2019-04-19 02:00 | 2019-07-08 02:00 | 2019 | Jul | 8 | FitBand Team | 6 | 32 | 5 | 1
Epic | RUBBERBALL-15 | Charger | To Do | RUBBERBALL-14 Power sources |  | 2019-04-24 02:00 | 2019-07-16 02:00 | 2019 | Jul | 16 | FitBand Team | 60 | 277 | 5 | 5
Story | FITBAND-30 | As a consumer, I want to be sure that my charger is touch safe | To Do |  | Charger | 2019-04-27 02:00 | 2019-07-16 02:00 | 2019 | Jul | 16 | FitBand Team | 48 | 243 | 3 | 3
Task | RUBBERBALL-17 | Use the Charger object to represent the events associated with a charger | To Do |  | Charger | 2019-05-03 02:00 | 2019-07-13 02:00 | 2019 | Jul | 13 | FitBand Team | 12 | 34 | 2 | 2
Initiative | FITBAND-54 | Sharing training data | Under development |  |  | 2019-05-07 02:00 | 2019-10-05 02:00 | 2019 | Oct | 5 | FitBand Team | 7 | 1383 | 26 | 1 | 3.846%
Epic | FITBAND-507 | Data transmission | To Do | FITBAND-54 Sharing training data |  | 2019-05-11 02:00 | 2019-10-05 02:00 | 2019 | Oct | 5 | Sensors Team | 39 | 1383 | 26 | 1
Task | FITBAND-48 | Data transfer between paired FitBand devices | Under development |  | Data transmission | 2019-05-14 02:00 | 2019-07-24 02:00 | 2019 | Jul | 24 | FitBand Team | 4 | 23 | 4 | 1
Task | FITBAND-13 | Transfer the data to the mobile device once a second | To Do |  | Data transmission | 2019-05-17 02:00 | 2019-08-05 02:00 | 2019 | Aug | 5 | FitBand Team | 4 | 342 | 5 | 0
Task | FITBAND-34 | Access FitBand through WiFi | To Do |  | Data transmission | 2019-05-25 02:00 | 2019-08-09 02:00 | 2019 | Aug | 9 | FitBand Team | 4 | 311 | 6 | 0
Bug | FITBAND-42 | Friend list upload process has failed with message "not in sync: resp=0×00" | Under development |  | Data transmission | 2019-05-30 02:00 | 2019-08-13 02:00 | 2019 | Aug | 13 | FitBand Team | 6 | 453 | 7 | 0
Story | FITBAND-47 | As a user, I want to see feedback from FitBand if the connection exists | Under development |  | Data transmission | 2019-06-02 02:00 | 2019-08-16 02:00 | 2019 | Aug | 16 | FitBand Team | 14 | 231 | 0 | 0
Task | FITBAND-29 | Connect FitBand-Bluetooth module | Under development |  | Data transmission | 2019-06-05 02:00 | 2019-07-07 02:00 | 2019 | Jul | 7 | Analytics Team | 7 | 23 | 4 | 0
Initiative | FITBAND-503 | Tracking training data | Under development |  |  | 2019-06-06 02:00 | 2019-11-19 01:00 | 2019 | Nov | 19 | FitBand Team | 7 | 2694 | 217 | 56 | 25.81%
Epic | FITBAND-4 | Data collection | Under development | FITBAND-503 Tracking training data |  | 2019-06-11 02:00 | 2019-10-05 02:00 | 2019 | Oct | 5 | FitBand Team | 91 | 926 | 21 | 9
Task | FITBAND-37 | Connect FitBand-Battery | Under development |  | Data collection | 2019-06-16 02:00 | 2019-08-07 02:00 | 2019 | Aug | 7 | FitBand Team | 4 | 22 | 3 | 0
Task | FITBAND-46 | Run [Serial Monitor] on FitBand IDE to check if the accelerometer works fine | Under development |  | Data collection | 2019-06-18 02:00 | 2019-08-07 02:00 | 2019 | Aug | 7 | FitBand Team | 6 | 321 | 2 | 1
Task | FITBAND-25 | With accelerometer measure x axis / y axis / z axis values | Under development |  | Data collection | 2019-06-22 02:00 | 2019-08-24 02:00 | 2019 | Aug | 24 | FitBand Team | 14 | 43 | 3 | 2
Task | FITBAND-6 | Android app check steps using collected data provided from FitBand | Under development |  | Data collection | 2019-06-25 02:00 | 2019-08-31 02:00 | 2019 | Aug | 31 | FitBand Team | 4 | 32 | 1 | 3
Task | FITBAND-8 | Save calorie data, so the progress can be monitored in a monthly/daily/hourly graph | To Do |  | Data collection | 2019-06-28 02:00 | 2019-09-05 02:00 | 2019 | Sep | 5 | FitBand Team | 6 | 231 | 5 | 2
Task | FITBAND-27 | Use Android app to find out an interval that user’s movement increase dramatically | To Do |  | Data collection | 2019-07-01 02:00 | 2019-09-11 02:00 | 2019 | Sep | 11 | FitBand Team | 4 | 243 | 4 | 1
Task | FITBAND-11 | Check the accelerometer data 20 times in every 1 second | To Do |  | Data collection | 2019-07-14 02:00 | 2019-09-29 02:00 | 2019 | Sep | 29 | FitBand Team | 14 | 34 | 3 | 0
Epic | FITBAND-474 | Metrics calculation | Under development | FITBAND-503 Tracking training data |  | 2019-07-16 02:00 | 2019-11-19 01:00 | 2019 | Nov | 19 | Analytics Team | 91 | 1768 | 196 | 47
Task | FITBAND-5 | Calculate calories and steps using sensor data | Under development |  | Metrics calculation | 2019-07-23 02:00 | 2019-09-18 02:00 | 2019 | Sep | 18 | Analytics Team | 14 | 45 | 3 | 1
Task | FITBAND-28 | Calculate burned calories based on user’s weight and steps, and accumulates data | Under development |  | Metrics calculation | 2019-07-27 02:00 | 2019-09-21 02:00 | 2019 | Sep | 21 | Analytics Team | 6 | 76 | 4 | 0
Task | FITBAND-52 | Gather cumulative burned calorie data every hour on Timeline | To Do |  | Metrics calculation | 2019-07-31 02:00 | 2019-10-06 02:00 | 2019 | Oct | 6 | Analytics Team | 4 | 700 | 171 | 38
Task | FITBAND-53 | Draw a graph from the data from the accelerometer | To Do |  | Metrics calculation | 2019-08-04 02:00 | 2019-10-22 02:00 | 2019 | Oct | 22 | Analytics Team | 7 | 129 | 1 | 0
Task | FITBAND-36 | Connect FitBand-Accelerometer | Under development |  | Metrics calculation | 2019-09-09 02:00 | 2019-10-20 02:00 | 2019 | Oct | 20 | Analytics Team | 14 | 234 | 3 | 2
Task | FITBAND-39 | Disconnect when idle | Under development |  | Metrics calculation | 2019-10-04 02:00 | 2019-10-29 01:00 | 2019 | Oct | 29 | Analytics Team | 14 | 43 | 5 | 0
Task | FITBAND-40 | Import metrics data | To Do |  | Metrics calculation | 2019-10-09 02:00 | 2019-10-25 02:00 | 2019 | Oct | 25 | Analytics Team | 14 | 67 | 4 | 1
Task | FITBAND-43 | Verify every module can use metrics readings | To Do |  | Metrics calculation | 2019-10-13 02:00 | 2019-10-29 01:00 | 2019 | Oct | 29 | Analytics Team | 4 | 231 | 2 | 2
Story | FITBAND-51 | As a user, I want to install the app, so I can pair the mobile device with FitBand | Under development |  | Metrics calculation | 2019-10-18 02:00 | 2019-11-19 01:00 | 2019 | Nov | 19 | Analytics Team | 7 | 243 | 3 | 3
Initiative | RUBBERBALL-9 | Next generation smart sensors | To Do |  |  | 2019-10-27 02:00 | 2020-06-03 02:00 | 2020 | Jun | 3 | FitBand Team | 52 | 2329 | 137 | 28 | 20.44%
Epic | RUBBERBALL-11 | Touch sensors | To Do | RUBBERBALL-9 Next generation smart sensors |  | 2019-11-10 01:00 | 2020-05-05 02:00 | 2020 | May | 5 | Sensors Team | 13 | 365 | 11 | 2
Task | RUBBERBALL-10 | Build in fingerprint sensor | To Do |  | Touch sensors | 2019-12-08 01:00 | 2020-01-26 01:00 | 2020 | Jan | 26 | Sensors Team | 6 | 342 | 5 | 0
Task | RUBBERBALL-12 | Add body temperature sensor | Under development |  | Touch sensors | 2019-12-18 01:00 | 2020-02-08 01:00 | 2020 | Feb | 8 | FitBand Team | 7 | 23 | 6 | 2
Epic | RUBBERBALL-13 | Body presence sensor | Under development | RUBBERBALL-9 Next generation smart sensors |  | 2019-12-27 01:00 | 2020-01-31 01:00 | 2020 | Jan | 31 | Sensors Team | 4 | 775 | 3 | 1
Task | FITBAND-506 | Allow to set sensor reading frequency | To Do |  | Body presence sensor | 2020-01-01 01:00 | 2020-01-31 01:00 | 2020 | Jan | 31 | Sensors Team | 4 | 775 | 2 | 0
Epic | FITBAND-469 | Movement sensors | To Do | RUBBERBALL-9 Next generation smart sensors |  | 2020-01-14 01:00 | 2020-04-01 02:00 | 2020 | Apr | 1 | FitBand Team | 23 | 277 | 6 | 2
Task | FITBAND-442 | Build in accelerometer | Under development |  | Movement sensors | 2020-01-30 01:00 | 2020-03-17 01:00 | 2020 | Mar | 17 | Sensors Team | 14 | 243 | 1 | 0
Task | FITBAND-447 | Build in tilt sensor | Under development |  | Movement sensors | 2020-02-10 01:00 | 2020-04-01 02:00 | 2020 | Apr | 1 | Sensors Team | 6 | 34 | 5 | 2
Epic | FITBAND-487 | Environmental sensors | Under development | RUBBERBALL-9 Next generation smart sensors |  | 2020-02-18 01:00 | 2020-06-03 02:00 | 2020 | Jun | 3 | Sensors Team | 12 | 912 | 117 | 23
Task | FITBAND-441 | Add environment temperature sensor | To Do |  | Environmental sensors | 2020-02-18 01:00 | 2020-05-04 02:00 | 2020 | May | 4 | Sensors Team | 3 | 342 | 3 | 2
Task | FITBAND-488 | Build in humidity sensor | To Do |  | Environmental sensors | 2020-02-23 01:00 | 2020-03-11 01:00 | 2020 | Mar | 11 | Sensors Team | 14 | 48 | 14 | 7
Task | FITBAND-489 | Add color sensor | Under development |  | Environmental sensors | 2020-02-28 01:00 | 2020-03-11 01:00 | 2020 | Mar | 11 | Sensors Team | 6 | 343 | 3 | 0
Task | FITBAND-490 | Introduce smoke and gas sensors | To Do |  | Environmental sensors | 2020-02-29 01:00 | 2020-03-16 01:00 | 2020 | Mar | 16 | Sensors Team | 7 | 22 | 4 | 1
Task | FITBAND-491 | Light sensor | To Do |  | Environmental sensors | 2020-03-04 01:00 | 2020-04-02 02:00 | 2020 | Apr | 2 | Sensors Team | 7 | 123 | 92 | 10
Task | FITBAND-492 | Ultrasonic sensor | To Do |  | Environmental sensors | 2020-03-09 01:00 | 2020-04-07 02:00 | 2020 | Apr | 7 | Sensors Team | 6 | 34 | 1 | 3
Initiative | FITBAND-500 | Smart home integrations | To Do |  |  | 2020-03-18 01:00 | 2020-07-07 02:00 | 2020 | Jul | 7 | FitBand Team | 7 | 952 | 35 | 2 | 5.714%
Epic | FITBAND-493 | Smart door integration | To Do | FITBAND-500 Smart home integrations |  | 2020-03-21 01:00 | 2020-06-20 02:00 | 2020 | Jun | 20 | FitBand Team | 39 | 522 | 9 | 0
Story | FITBAND-495 | As a user, I want my FitBand tracker to integrate with my Smart Home system, so I can control my front door | To Do |  | Smart door integration | 2020-03-25 01:00 | 2020-04-23 02:00 | 2020 | Apr | 23 | FitBand Team | 14 | 34 | 2 | 0
Task | FITBAND-494 | Integrate the Smart Door lock protocol in FitBand source code | To Do |  | Smart door integration | 2020-03-26 01:00 | 2020-04-24 02:00 | 2020 | Apr | 24 | FitBand Team | 7 | 343 | 1 | 2
Task | FITBAND-497 | Show alerts on FitBand screen, when Smart Door is opened | To Do |  | Smart door integration | 2020-04-01 02:00 | 2020-04-30 02:00 | 2020 | Apr | 30 | FitBand Team | 4 | 22 | 1 | 1
Task | FITBAND-498 | Add ability to open and lock front door from FitBand | Under development |  | Smart door integration | 2020-04-05 02:00 | 2020-05-04 02:00 | 2020 | May | 4 | FitBand Team | 14 | 123 | 5 | 0
Epic | FITBAND-504 | Smart appliances integration | To Do | FITBAND-500 Smart home integrations |  | 2020-04-06 02:00 | 2020-07-07 02:00 | 2020 | Jul | 7 | FitBand Team | 7 | 430 | 26 | 2
Story | FITBAND-505 | As a user, I want my FitBand to integrate with Smart Home system, so I can control home appliances | To Do |  | Smart appliances integration | 2020-06-03 02:00 | 2020-07-03 02:00 | 2020 | Jul | 3 | FitBand Team | 4 | 65 | 12 | 0
Task | FITBAND-499 | Add Smart Coffee Machine control panel to the FitBand interface | Under development |  | Smart appliances integration | 2020-06-06 02:00 | 2020-07-06 02:00 | 2020 | Jul | 6 | FitBand Team | 7 | 343 | 8 | 0
Task | FITBAND-41 | Add ability to control the Smart Window blinds and shades from FitBand | Under development |  | Smart appliances integration | 2020-06-10 02:00 | 2020-07-07 02:00 | 2020 | Jul | 7 | FitBand Team | 4 | 22 | 6 | 4
60
Created at 28/Jun/19 12:37 PM by Levente Szabo with Better Excel Exporter for Jira
help »