## Issue Navigator
Key | T | Project | Summary | P | Assignee | Status | Resolution | Creator | Created | Start Date | End Date | Labels | Sprint | Story Points | Links | Updated | Resolved | Affects Version/s | Fix Version/s | Components | Due | Watchers | Description | Progress | Σ Progress | Σ Time Spent | Σ Remaining Estimate | Σ Original Estimate
B4B-26 | Story | Beem for Business | Set up Hootsuite account | Medium | Casey Ford | To Do |  | Levente Szabo | 2012-05-17 12:57 | 2012-06-12 | 2012-06-12 | CRM, marketing | Marketing and customer rel | 2 |  | 2012-12-15 11:25 | 2012-09-20 17:17 |  |  | Landing Page, website design |  | 1 | We are launching beem4biz.com! To determine what still has to be done, check the progress of the subtasks below. |  | 86% | 595.7667 | 91.8833
B4B-29 | Task | Beem for Business | Plan the email campaigns | Medium | Levente Szabo | Done | Done | Levente Szabo | 2012-05-17 13:02 | 2012-06-13 | 2012-06-20 | CRM, marketing | Marketing and customer rel | 6 |  | 2012-12-05 11:08 |  |  |  | Landing Page, website design |  | 1 | Develop the main video feed where the created videos can be seen and shared.
B4B-28 | Sub-task | Beem for Business | Copy for email campaigns | Low | Casey Ford | To Do |  | Levente Szabo | 2012-05-17 13:01 | 2012-06-13 | 2012-06-20 | CRM, marketing | Marketing and customer rel | 8 |  | 2012-12-05 11:07 |  |  |  | Android App, iOS App |  | 1 | Users can interact w/ videos by Reacting to them. This shoots and posts a front-camera image.
B4B-30 | Task | Beem for Business | Set up FB group for beta testers | Medium | Casey Ford | To Do |  | Levente Szabo | 2012-05-17 13:06 | 2012-05-29 | 2012-05-29 | CRM, marketing | Marketing and customer rel | 6 |  | 2012-09-18 15:38 |  |  |  | Landing Page, website design |  | 1 | Create the first email campaign copy contents. This should cover the launch and the concept and appreciating the early bird users.
B4B-27 | Story | Beem for Business | Set up Mailchimp | Low | Casey Ford | In Progress |  | Levente Szabo | 2012-05-17 12:58 | 2012-06-12 | 2012-06-12 | CRM, marketing | Marketing and customer rel | 8 |  | 2012-12-06 14:56 |  |  |  | Android App, iOS App |  | 1 | Separate email campaign for the public and the early bird users | 100% | 100% | 3 | 0
B4B-24 | Sub-task | Beem for Business | Video feed | Medium | Dalia Lens | Done | Done | Levente Szabo | 2012-05-17 12:54 | 2012-06-06 | 2012-06-09 | DEV, IT | Dev sprint | 6 |  | 2012-12-05 11:43 |  |  |  | Landing Page, website design |  | 1 | Collect feedback from users to analyse and review | 0% | 0% |  | 0
B4B-23 | Sub-task | Beem for Business | Video sharing feature | Low | Robert Mongose | To Do |  | Levente Szabo | 2012-05-17 12:53 | 2012-06-02 | 2012-06-06 | DEV, IT | Dev sprint | 8 |  | 2012-12-05 11:24 | 2012-09-20 16:49 |  |  | Landing Page, website design |  | 1 |  | 0% | 0% |  | 0
B4B-22 | Sub-task | Beem for Business | Video recording feature | Medium | Robert Mongose | To Do |  | Levente Szabo | 2012-05-17 12:52 | 2012-05-29 | 2012-06-02 | DEV, IT | Dev sprint | 4 |  | 2012-12-05 11:13 | 2012-09-20 16:49 |  |  | Android App, iOS App |  | 1
B4B-21 | Epic | Beem for Business | Implement MVP functions | Medium | Levente Szabo | Done | Done | Levente Szabo | 2012-05-17 12:40 | 2012-05-10 | 2012-05-26 | DEV, IT | Dev sprint | 4 |  | 2012-12-05 11:12 | 2012-09-20 16:49 |  |  | Landing Page, website design |  | 1
B4B-20 | Sub-task | Beem for Business | Log-in form | Medium | Robert Mongose | To Do |  | Levente Szabo | 2012-05-16 11:04 | 2012-05-24 | 2012-05-26 | DEV, IT | Dev sprint | 4 |  | 2012-12-06 14:47 | 2012-05-22 11:19 |  |  | Android App, iOS App |  | 1 |  | 100% | 100% | 59.2 | 0
B4B-19 | Sub-task | Beem for Business | Sign-up form | Medium | Levente Szabo | In Progress |  | Levente Szabo | 2012-05-16 11:03 | 2012-05-22 | 2012-05-24 | DEV, IT | Dev sprint | 4 | B4B-9 | 2012-12-05 11:15 | 2012-05-22 14:46 |  |  | Landing Page, website design |  | 1 |  | 100% | 100% | 80 | 0
B4B-25 | Sub-task | Beem for Business | "React" feature | Medium | Dalia Lens | To Do |  | Levente Szabo | 2012-05-17 12:55 | 2012-06-09 | 2012-06-13 | DEV, IT | Dev sprint | 6 |  | 2012-12-06 14:45 | 2012-05-22 11:18 |  |  | Android App, iOS App |  | 1 |  | 100% | 100% | 85 | 0
B4B-16 | Task | Beem for Business | Set up Dev Environment | Medium | Robert Mongose | Done | Done | Levente Szabo | 2012-05-16 10:52 | 2012-05-11 | 2012-05-15 | DEV, IT | Dev sprint | 8 |  | 2012-12-05 11:19 | 2012-07-18 15:51 |  |  | Android App, iOS App |  | 1 |  | 50% | 50% | 80 | 80
B4B-18 | Sub-task | Beem for Business | Tutorial section | Medium | Dalia Lens | Done | Done | Levente Szabo | 2012-05-16 10:59 | 2012-05-16 | 2012-05-22 | DEV, IT | Dev sprint | 14 |  | 2012-12-06 14:21 |  |  |  | Landing Page, website design |  | 1 | Create a platform for communication with beta testers. | 100% | 100% | 21 | 0
B4B-17 | Task | Beem for Business | Set up cloud hosting | Low | Robert Mongose | Done | Done | Levente Szabo | 2012-05-16 10:54 | 2012-05-15 | 2012-05-15 | DEV, IT | Dev sprint | 18 |  | 2012-12-06 14:58 |  |  |  | Android App, iOS App |  | 1 | Set up Mailchimp for email marketing | 100% | 100% | 8.8333 | 0
B4B-15 | Task | Beem for Business | Set up DB | Medium | Robert Mongose | Done | Done | Levente Szabo | 2012-05-16 10:51 | 2012-05-10 | 2012-05-10 | DEV, IT | Dev sprint | 4 |  | 2012-07-14 14:19 |  |  |  | Landing Page, website design |  | 1 | Set up the tools for social media operations
B4B-11 | Task | Beem for Business | Landing page copy | Medium | Dalia Lens | In Progress |  | Levente Szabo | 2012-05-14 19:47 | 2012-05-31 | 2012-06-02 | billable, web | Landing page sprint | 6 | B4B-12 | 2012-12-15 15:15 | 2012-07-18 15:51 |  |  | Android App, iOS App |  | 1 | Develop the main video feed where the created videos can be seen and shared. | 100% | 100% | 27 | 0 | 0
B4B-49 | Task | Beem for Business | Beem Inc. - Company website design | Highest | Dalia Lens | Done | Done | Levente Szabo | 2012-07-13 17:11 | 2012-05-08 | 2012-05-23 | billable |  | 24 |  | 2012-12-05 11:02 |  |  |  | Landing Page, website design |  | 1 | Let's ship the Video sharing feature
B4B-8 | Task | Beem for Business | Design Feedback (1.) | Medium | Dalia Lens | Done | Done | Levente Szabo | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | interactions, user-experience, user-interface | UX&UI sprint | 6 | B4B-4, B4B-6, B4B-7 | 2012-12-05 11:01 |  |  |  | Landing Page, website design |  | 1 | The video recording feature is the core feature of the MVP so we need to ensure that we deliver this in great quality and on time! Guys, for starters, make sure that when you call the FpsRate getter the stream isn't null, the feature will only work this way! If you have any questions pls turn immediately to me or [~robert], he is an expert on this. {code:java} public int getFpsRate() { return stream.fpsRate; } {code} | 100% | 100% | 32 | 0
B4B-10 | Task | Beem for Business | Design Feedback (3.) | Medium | Dalia Lens | To Do |  | Levente Szabo | 2012-05-14 19:42 | 2012-05-23 | 2012-05-23 | user-experience, user-interface | UX&UI sprint | 2 | B4B-9 | 2012-12-06 14:16 | 2012-06-09 10:09 |  |  |  |  | 1 | Implement the first functions using the graphic design. | 69% | 78% | 159.5667 | 45 | 0
B4B-9 | Task | Beem for Business | Design Feedback (2.) | Medium | Dalia Lens | Done | Done | Levente Szabo | 2012-05-14 19:36 | 2012-05-16 | 2012-05-16 | user-experience, user-interface | UX&UI sprint | 4 | B4B-19, B4B-10 | 2012-12-05 11:32 | 2012-09-20 16:49 |  |  |  |  | 1 | Create the log-in form
B4B-7 | Task | Beem for Business | Graphic designer briefing (1.) | High | Dalia Lens | Done | Done | Levente Szabo | 2012-05-14 19:18 | 2012-06-02 | 2012-06-02 | user-experience, user-interface | UX&UI sprint | 4 | B4B-6, B4B-8 | 2012-12-05 11:32 | 2012-09-20 16:50 |  |  |  |  | 1 | Create the registration form | 100% | 100% | 16 | 0
B4B-4 | Task | Beem for Business | Validation landing page | Highest | Owen Klyed | Done | Done | Levente Szabo | 2012-05-14 18:44 | 2012-05-17 | 2012-05-17 | validation | BVP Validation Sprint | 2 | B4B-3, B4B-8 | 2012-12-05 11:40 | 2012-05-22 14:46 |  |  | Landing Page, website design |  | 1 | Implement and test pre-registration intro/tutorial section | 100% | 100% | 40 | 0
B4B-3 | Task | Beem for Business | Customer interviews | Highest | Owen Klyed | Done | Done | Levente Szabo | 2012-05-14 18:40 | 2012-05-16 | 2012-05-30 | validation | BVP Validation Sprint | 72 | B4B-4, B4B-5 | 2012-08-09 11:39 | 2012-05-22 14:45 |  |  | Landing Page, website design |  | 1 | Set up the Amazon cloud hosting service
B4B-5 | Task | Beem for Business | Traditional market research | Lowest | Owen Klyed | Done | Done | Levente Szabo | 2012-05-14 18:48 | 2012-05-16 | 2012-05-30 | validation | BVP Validation Sprint | 22 | B4B-3, B4B-6 | 2012-12-06 14:39 | 2012-05-22 14:44 |  |  | Landing Page, website design |  | 1 | Set up the development environment for all coders. Install all software needed | 100% | 100% | 2.4167 | 0
B4B-6 | Task | Beem for Business | MVP functionality | High | Owen Klyed | Done | Done | Levente Szabo | 2012-05-14 18:50 | 2012-05-31 | 2012-06-02 | validation | BVP Validation Sprint | 6 | B4B-7, B4B-8, B4B-5 | 2012-12-06 14:22 | 2012-05-22 14:44 |  |  | Landing Page, website design |  | 1 | Set up database for application | 100% | 100% | 3 | 0
B4B-1 | Task | Beem for Business | Secure and buy the domain name | Low | Dalia Lens | Done | Done | Levente Szabo | 2012-05-11 11:50 | 2012-05-16 | 2012-05-16 | web | Dev sprint | 4 |  | 2012-12-05 11:29 | [5 empty] | 1 | Based on design and copy version testing create final landing page for the service, optimized for conversion and social sharing. | 100% | 48% | 165.4583 | 175
B4B-13 | Task | Beem for Business | Decision on landing page design | Medium | Dalia Lens | In Progress |  | Levente Szabo | 2012-05-14 21:36 | 2012-06-19 | 2012-06-19 | web | Landing page sprint | 6 | B4B-12, B4B-14 | 2012-12-05 11:25 | 2012-09-20 16:50 |  |  | Landing Page |  | 1 | This is an *All-Hands decision* so all team members are welcome to weigh in with their opinion in the comment section. Please share your view in the comments {color:red}on all components{color}, namely the copy, the design, the timing, the highlighted features, so we can have everyone's opinion in one place. By the decision time we will have had many debates, A/B tests and some UX tests run so we should have enough data to work with.
B4B-12 | Task | Beem for Business | A/B test landing page | Low | Dalia Lens | In Progress |  | Levente Szabo | 2012-05-14 19:50 | 2012-06-05 | 2012-06-19 | web | Landing page sprint | 8 | B4B-11, B4B-13 | 2012-12-06 14:51 | 2012-09-20 16:50 |  |  | Android App, iOS App |  | 1 | A/B test the future landing page copy texts with Unbounce. | 100% | 100% | 82.7583 | 0
B4B-14 | Task | Beem for Business | Create landing page | Medium | Dalia Lens | To Do |  | Levente Szabo | 2012-05-14 21:41 | 2012-06-20 | 2012-06-22 | web | Landing page sprint | 6 | B4B-13 | 2012-12-06 14:48 | 2012-09-20 16:50 |  |  |  |  | 1 | Create Copy content for the real landing page. That content will help decide on the landing page design later. | 100% | 100% | 93.75 | 0
B4B-32 | Sub-task | Beem for Business | Feedback on overall design approach | Medium | Owen Klyed | Done | Done | Levente Szabo | 2012-05-17 15:25 | 2012-06-20 | 2012-06-22 | web | UX&UI sprint | 6 |  | 2012-12-05 11:38 | 2012-09-20 16:49 |  |  | Android App, iOS App |  | 1 | Third graphic designer meeting and feedback/follo-up. By this time we need the rest of the MVP app screens: Video feed, notifications, profile screen, favorites screen.
B4B-31 | Task | Beem for Business | Collect feedback | Low | Casey Ford | To Do |  | Levente Szabo | 2012-05-17 13:07 | 2012-06-14 | 2012-06-14 |  | Marketing and customer rel | 8 |  | 2012-12-05 11:22 | 2012-07-13 18:02 |  |  |  |  | 1 | Second feedback meeting with designers. By this time we should have the following screen designs: pre-reg tutorial section, reg form, log-in screen
B4B-34 | Sub-task | Beem for Business | Clarify color schemes | Medium | Casey Ford | In Progress |  | Levente Szabo | 2012-05-19 11:39 | 2012-06-20 | 2012-06-22 |  | UX&UI sprint | 2 |  | 2012-12-05 11:13 |  |  |  | Android App, iOS App, Landing Page |  | 2 | _To be present: UI project team lead, product manager, designers. Please come prepared!_ (on) +*First design feedback meeting*+ During the meeting with the designer team, we need to cover the following: * Make sure they understood the business concept * Feedback to the first design mockup. {color:red}Give follow-up briefing if needed{color} (most probably needed :)) * Request corrective actions and/or clear out all remaining concerns | 100% | 100% | 2 | 0
B4B-33 | Sub-task | Beem for Business | Feedback on components | Medium | Dalia Lens | To Do |  | Levente Szabo | 2012-05-17 15:26 | 2012-06-20 | 2012-06-22 |  | UX&UI sprint | 2 |  | 2012-12-06 14:43 | 2012-05-22 15:01 |  |  |  |  | 1 | Besides the Lean Method we will research the market for existing solutions and players on the market and determine how those offerings are different from ours. Need to also pinpoint their shortcomings and weaknesses too. | 86% | 86% | 74.9167 | 11.8833
B4B-55 | Sub-task | Beem for Business | Brand color scheme | Medium |  | To Do |  | Levente Szabo | 2012-07-21 13:51 | 2012-05-08 | 2012-05-10 |  |  | 4 |  | 2012-12-12 17:10 | 2012-05-24 14:22 |  |  |  |  | 1 | Set up a validation landing page using Javelin.com. We need to test and measure how attractive is our current offering. | 2% | 2% | 4.9 | 175
B4B-58 | Sub-task | Beem for Business | Website layout | Medium |  | To Do |  | Levente Szabo | 2012-07-21 13:53 | 2012-05-18 | 2012-05-23 |  |  | 6 |  | 2012-12-05 11:23 | 2012-05-19 16:04 |  |  |  |  | 1 | As an essential part of our idea validation process we need at lease 50 interview conducted and documented. The interviews need to follow the ""Lean Startup Methodology". | 100% | 100% | 120.9 | 0
B4B-57 | Sub-task | Beem for Business | Second mockup | Medium |  | To Do |  | Levente Szabo | 2012-07-21 13:52 | 2012-05-14 | 2012-05-18 |  |  | 4 |  | 2012-05-22 14:45 | 2012-05-22 14:45 |  |  |  |  | 1 | We need to make sure that we have the domain name rights and all social media accounts.
B4B-56 | Sub-task | Beem for Business | First mockup | Medium |  | To Do |  |  | 2012-07-21 13:52 | 2012-05-10 | 2012-05-14 |  |  | 4
B4B-36 | Sub-task | Beem for Business | Phone interviews | Medium | Owen Klyed | Done | Done |  | 2012-05-19 13:38 | 2012-05-25 | 2012-05-30 |  | BVP Validation Sprint | 40
B4B-35 | Sub-task | Beem for Business | In person interviews | Medium | Owen Klyed | Done | Done |  | 2012-05-19 13:36 | 2012-05-16 | 2012-05-26 |  | BVP Validation Sprint | 40
B4B-38 | Sub-task | Beem for Business | Historical analysis | Low | Dalia Lens | Done | Done |  | 2012-05-19 13:44 | 2012-05-22 | 2012-05-30 |  | BVP Validation Sprint | 22
B4B-37 | Sub-task | Beem for Business | Online research | Low | Owen Klyed | Done | Done |  | 2012-05-19 13:44 | 2012-05-16 | 2012-05-22 |  | BVP Validation Sprint | 30
42 | [13 empty] | 450 | [7 empty] | 38 |  |  |  | 1757.4667 | 578.7667 | 0