## Issue Navigator
Key | Project | Summary | P | Assignee | Status | Resolution | Created | Start Date | End Date | Change Author | Change Time | Changed Field | Old value | New Value
B4B-56 | Beem for Business | First mockup | Medium | Dalia Lens | To Do |  | 2012-07-21 13:52 | 2012-05-10 | 2012-05-14 | Dalia Lens | 2012-08-09 11:42 | Story Points |  | 4
B4B-55 | Beem for Business | Brand color scheme | Medium | Dalia Lens | To Do |  | 2012-07-21 13:51 | 2012-05-08 | 2012-05-10 | Levente Szabo | 2012-08-09 11:42 | Story Points |  | 4
B4B-49 | Beem for Business | Beem Inc. - Company website design | Highest | Dalia Lens | Done | Done | 2012-07-13 17:11 | 2012-05-08 | 2012-05-23 | Levente Szabo | 2012-07-13 17:17 | Attachment |  | mockup.png
[10 empty] | Richard Dawkins | 2012-07-11 17:18 | Attachment |  | mockup2.png
[10 empty] | Richard Dawkins | 2012-07-12 17:18 | Attachment |  | mockup3.png
[10 empty] | Levente Szabo | 2012-07-13 17:18 | labels |  | billable design website
[10 empty] | Levente Szabo | 2012-07-13 17:18 | priority | Medium | Highest
[10 empty] | Levente Szabo | 2012-07-13 17:18 | status | To Do | In Progress
[10 empty] | Levente Szabo | 2012-07-13 17:18 | assignee |  | Dalia Lens
[10 empty] | Dalia Lens | 2012-07-13 17:19 | summary | Beem website design | Beem Inc. - Company website design
[10 empty] | Robert Mongose | 2012-07-13 17:22 | description |  | Full website design for Beem Inc. based on the attached brief. Timeline is found in the brief, additional visual assets are available at the company.
[10 empty] | Levente Szabo | 2012-07-13 17:23 | Attachment |  | Beem website proejct- Design Brief.doc
[10 empty] | Owen Klyed | 2012-07-13 17:23 | Attachment | Beem website proejct- Design Brief.doc
B4B-38 | Beem for Business | Historical analysis | Low | Dalia Lens | Done | Done | 2012-05-19 13:44 | 2012-05-22 | 2012-05-30 | Levente Szabo | 2012-05-19 13:47 | priority | Medium | Low
[10 empty] | Levente Szabo | 2012-05-19 14:37 | status | To Do | In Progress
[10 empty] | Marcus Thiel | 2012-05-22 11:19 | resolution |  | Done
B4B-37 | Beem for Business | Online research | Low | Owen Klyed | Done | Done | 2012-05-19 13:44 | 2012-05-16 | 2012-05-22 | Levente Szabo | 2012-05-19 13:46 | priority | Medium | Low
[10 empty] | Casey Ford | 2012-05-19 16:03 | status | To Do | In Progress
[10 empty] | Casey Ford | 2012-05-22 14:24 | assignee |  | Owen Klyed
[10 empty] | Owen Klyed | 2012-05-22 14:46 | resolution |  | Done
[12 empty] | status | In Progress | Done
[10 empty] | Owen Klyed | 2012-08-09 11:43 | Story Points |  | 30
[10 empty] | Owen Klyed | 2012-08-11 14:56 | labels |  | validation
B4B-36 | Beem for Business | Phone interviews | Medium | Owen Klyed | Done | Done | 2012-05-19 13:38 | 2012-05-25 | 2012-05-30 | Levente Szabo | 2012-05-19 13:43 | status | To Do | In Progress
[10 empty] | Owen Klyed | 2012-05-19 16:03 | resolution |  | Done
[12 empty] | status | In Progress | Done
[10 empty] | Owen Klyed | 2012-05-19 16:04 | resolution | Done
[12 empty] | status | Done | In Progress
[10 empty] | Levente Szabo | 2012-05-19 16:39 | timeestimate |  | 0
[12 empty] | timespent |  | 144000
[12 empty] | WorklogId | 10403
[10 empty] | Levente Szabo | 2012-05-22 11:18 | resolution |  | Done
[12 empty] | status | In Progress | Done
[10 empty] | Dalia Lens | 2012-05-22 14:20 | summary | Phone intervies | Phone interviews
[10 empty] | Levente Szabo | 2012-05-22 14:24 | assignee |  | Owen Klyed
[10 empty] | Levente Szabo | 2012-08-09 11:43 | Story Points |  | 40
[10 empty] | Levente Szabo | 2012-08-11 14:56 | labels |  | validation
B4B-35 | Beem for Business | In person interviews | Medium | Owen Klyed | Done | Done | 2012-05-19 13:36 | 2012-05-16 | 2012-05-26 | Owen Klyed | 2012-05-19 13:37 | End Date | 24/May/16 | 27/May/16
[10 empty] | Levente Szabo | 2012-05-19 13:42 | status | To Do | In Progress
[10 empty] | Robert Mongose | 2012-05-19 16:04 | resolution |  | Done
[12 empty] | status | In Progress | Done
[10 empty] | Robert Mongose | 2012-05-19 16:04 | resolution | Done
[12 empty] | status | Done | In Progress
[10 empty] | Robert Mongose | 2012-05-19 16:40 | timeestimate |  | 0
[12 empty] | timespent |  | 600
[12 empty] | WorklogId | 10301
[10 empty] | Owen Klyed | 2012-05-19 16:41 | timespent | 600 | 288000
[12 empty] | WorklogId | 10301
[10 empty] | Dalia Lens | 2012-05-22 10:09 | labels |  | billable
[10 empty] | Owen Klyed | 2012-05-22 10:09 | timespent | 288000 | 576000
[12 empty] | WorklogId | 10400
[10 empty] | Owen Klyed | 2012-05-22 10:14 | timeestimate | 0 | 288000
[12 empty] | timespent | 576000 | 288000
[12 empty] | WorklogId | 10301
[12 empty] | WorklogTimeSpent | 2 weeks
[10 empty] | Dalia Lens | 2012-05-22 10:16 | WorklogId | 10400
[10 empty] | Levente Szabo | 2012-05-22 10:32 | WorklogId | 10400
[10 empty] | Levente Szabo | 2012-05-22 11:18 | resolution |  | Done
[12 empty] | status | In Progress | Done
[10 empty] | Richard Dawkins | 2012-05-22 14:03 | labels | billable
[10 empty] | Levente Szabo | 2012-05-22 14:25 | assignee |  | Owen Klyed
[10 empty] | Levente Szabo | 2012-07-13 16:17 | resolution | Done
[10 empty] | Levente Szabo |  | status | Done | In Progress
[10 empty] | Levente Szabo | 2012-07-18 15:51 | resolution |  | Done
[12 empty] | status | In Progress | Done
[10 empty] | Robert Mongose | 2012-08-09 11:43 | Story Points |  | 40
B4B-34 | Beem for Business | Clarify color schemes | Medium | Casey Ford | In Progress |  | 2012-05-19 11:39 |  |  | Levente Szabo | 2012-05-19 11:40 | assignee |  | Dalia Lens
[10 empty] | Owen Klyed | 2012-05-19 11:40 | assignee | Dalia Lens | Casey Ford
[10 empty] | Levente Szabo | 2012-05-23 13:01 | Story Points |  | 2
[10 empty] | Levente Szabo | 2012-07-18 16:50 | resolution |  | Done
[12 empty] | status | To Do | Done
[10 empty] | Levente Szabo |  | status | Done | Done
[10 empty] | Casey Ford | 2012-07-18 16:54 | resolution | Done
[12 empty] | status | Done | In Progress
B4B-33 | Beem for Business | Feedback on components | Medium | Dalia Lens | To Do |  | 2012-05-17 15:26 |  |  | Owen Klyed | 2012-05-18 12:29 | assignee |  | Dalia Lens
[10 empty] | Levente Szabo | 2012-05-23 13:01 | Story Points |  | 2
B4B-32 | Beem for Business | Feedback on overall design approach | Medium | Owen Klyed | Done | Done | 2012-05-17 15:25 |  |  | Levente Szabo | 2012-05-18 12:29 | assignee |  | Dalia Lens
[10 empty] | Dalia Lens | 2012-05-18 18:17 | assignee | Dalia Lens | Robert Mongose
[10 empty] | Levente Szabo | 2012-05-19 11:56 | assignee | Robert Mongose | Owen Klyed
[10 empty] | Levente Szabo | 2012-05-23 13:02 | Story Points |  | 6
[10 empty] | Owen Klyed | 2012-07-13 16:17 | status | To Do | In Progress
[10 empty] | Levente Szabo | 2012-07-18 15:51 | resolution |  | Done
[12 empty] | status | In Progress | Done
B4B-31 | Beem for Business | Collect feedback | Low | Casey Ford | To Do |  | 2012-05-17 13:07 | 2012-06-14 | 2012-06-14 | Marcus Thiel | 2012-05-17 13:29 | Sprint |  | Dev sprint 2
[10 empty] | Levente Szabo | 2012-05-17 13:29 | Rank |  | Ranked higher
[10 empty] | Casey Ford | 2012-05-17 13:29 | Rank |  | Ranked lower
[10 empty] | Casey Ford | 2012-05-18 13:43 | priority | Medium | Low
[10 empty] | Owen Klyed | 2012-05-23 13:03 | Story Points |  | 8
[10 empty] | Levente Szabo | 2012-08-11 14:56 | labels |  | validation
B4B-30 | Beem for Business | Set up FB group for beta testers | Medium | Casey Ford | To Do |  | 2012-05-17 13:06 | 2012-05-29 | 2012-05-29 | Levente Szabo | 2012-05-17 13:29 | Sprint |  | Dev sprint 2
[10 empty] | Levente Szabo | 2012-05-17 13:29 | Rank |  | Ranked higher
[10 empty] | Dalia Lens | 2012-05-23 13:02 | Story Points |  | 6
[10 empty] | Levente Szabo | 2012-07-14 14:19 | labels | CR&mrktg | CRM marketing
[10 empty] | Levente Szabo | 2012-08-11 14:57 | labels | CRM marketing | CRM marketing validation
B4B-29 | Beem for Business | Plan the email campaigns | Medium | Levente Szabo | Done | Done | 2012-05-17 13:02 | 2012-06-13 | 2012-06-20 | Owen Klyed | 2012-05-17 13:29 | Sprint |  | Dev sprint 2
[10 empty] | Levente Szabo | 2012-05-17 13:29 | Rank |  | Ranked higher
[11 empty] | 2012-05-23 13:02 | Story Points |  | 6
[10 empty] | Marcus Thiel | 2012-06-08 11:31 | assignee | Casey Ford | Levente Szabo
[10 empty] | Levente Szabo | 2012-06-08 11:35 | assignee | Levente Szabo | Casey Ford
[10 empty] | Casey Ford | 2012-06-08 11:41 | assignee | Casey Ford | Levente Szabo
[10 empty] | Casey Ford | 2012-06-08 11:43 | resolution |  | Done
[12 empty] | status | To Do | Done
[10 empty] | Levente Szabo | 2012-06-08 11:45 | status | Done | Done
[10 empty] | Levente Szabo | 2012-06-08 11:46 | resolution | Done
[12 empty] | status | Done | In Progress
[10 empty] | Levente Szabo | 2012-06-08 11:46 | resolution |  | Done
[12 empty] | status | In Progress | Done
[10 empty] | Levente Szabo | 2012-07-13 16:17 | resolution | Done
[12 empty] | status | Done | In Progress
[10 empty] | Levente Szabo | 2012-07-14 14:19 | labels | CR&mrktg | CRM marketing
[10 empty] | Levente Szabo | 2012-07-18 15:51 | resolution |  | Done
[12 empty] | status | In Progress | Done
[10 empty] | Levente Szabo | 2012-08-11 14:57 | labels | CRM marketing | CRM marketing validation
B4B-28 | Beem for Business | Copy for email campaigns | Low | Casey Ford | To Do |  | 2012-05-17 13:01 | 2012-06-13 | 2012-06-20 | Levente Szabo | 2012-05-17 13:02 | Parent |  | B4B-29
[12 empty] | issuetype | Task | Sub-task
[10 empty] | Levente Szabo | 2012-05-18 13:43 | priority | Medium | Low
[10 empty] | Levente Szabo | 2012-05-23 13:03 | Story Points |  | 8
[10 empty] | Levente Szabo | 2012-07-14 14:19 | labels | CR&mrktg | CRM marketing
B4B-27 | Beem for Business | Set up Mailchimp | Low | Casey Ford | In Progress |  | 2012-05-17 12:58 | 2012-06-12 | 2012-06-12 | Levente Szabo | 2012-05-17 13:29 | Rank |  | Ranked lower
[10 empty] | Levente Szabo | 2012-05-17 13:29 | Sprint |  | Dev sprint 2
[10 empty] | Levente Szabo | 2012-05-17 13:29 | Rank |  | Ranked higher
[10 empty] | Levente Szabo | 2012-05-17 13:29 | Rank |  | Ranked lower
[10 empty] | Levente Szabo | 2012-05-18 13:42 | priority | Medium | Low
[10 empty] | Levente Szabo | 2012-05-23 13:03 | Story Points |  | 8
[10 empty] | Levente Szabo | 2012-07-13 16:17 | status | To Do | In Progress
[10 empty] | Levente Szabo | 2012-07-14 14:19 | labels | CR&mrktg | CRM marketing
[10 empty] | Levente Szabo | 2012-08-09 11:29 | timeestimate |  | 0
[12 empty] | timespent |  | 18000
[12 empty] | WorklogId | 20500
[10 empty] | Levente Szabo | 2012-08-09 11:29 | summary | Set up Maichimp | Set up Mailchimp
B4B-26 | Beem for Business | Set up Hootsuite account | Medium | Casey Ford | To Do |  | 2012-05-17 12:57 | 2012-06-12 | 2012-06-12 | Levente Szabo | 2012-05-17 13:29 | Sprint |  | Dev sprint 2
[10 empty] | Levente Szabo | 2012-05-23 13:01 | Story Points |  | 2
[10 empty] | Levente Szabo | 2012-07-14 14:19 | labels | CR&mrktg | CRM marketing
B4B-25 | Beem for Business | "React" feature | Medium | Dalia Lens | To Do |  | 2012-05-17 12:55 | 2012-06-09 | 2012-06-13 | Levente Szabo | 2012-05-18 15:14 | summary | Create the "React" feature | "React" feature
[10 empty] | Levente Szabo | 2012-05-18 16:25 | timeestimate |  | 0
[12 empty] | timespent |  | 115200
[12 empty] | WorklogId | 10202
[10 empty] | Levente Szabo | 2012-05-23 13:02 | Story Points |  | 6
[10 empty] | Levente Szabo | 2012-06-08 16:53 | assignee | Robert Mongose
[10 empty] | Levente Szabo | 2012-06-08 17:15 | timeoriginalestimate |  | 0
[12 empty] | assignee |  | Dalia Lens
[10 empty] | Levente Szabo | 2012-07-14 14:20 | labels | IT&Dev | DEV IT
B4B-24 | Beem for Business | Video feed | Medium | Dalia Lens | Done | Done | 2012-05-17 12:54 | 2012-06-06 | 2012-06-09 | Levente Szabo | 2012-05-18 15:14 | summary | Implement video feed | Video feed
[10 empty] | Levente Szabo | 2012-05-18 16:31 | timeestimate |  | 0
[12 empty] | timespent |  | 86400
[12 empty] | WorklogId | 10203
[10 empty] | Levente Szabo | 2012-05-23 13:02 | Story Points |  | 6
[10 empty] | Levente Szabo | 2012-06-08 16:53 | assignee | Robert Mongose
[10 empty] | Levente Szabo | 2012-06-08 17:15 | timeoriginalestimate |  | 0
[12 empty] | assignee |  | Dalia Lens
[10 empty] | Levente Szabo | 2012-07-13 16:17 | status | To Do | In Progress
[10 empty] | Levente Szabo | 2012-07-14 14:20 | labels | IT&Dev | DEV IT
[10 empty] | Levente Szabo | 2012-07-18 15:51 | resolution |  | Done
[12 empty] | status | In Progress | Done
B4B-23 | Beem for Business | Video sharing feature | Low | Robert Mongose | To Do |  | 2012-05-17 12:53 | 2012-06-02 | 2012-06-06 | Levente Szabo | 2012-05-18 13:49 | priority | Medium | Low
[10 empty] | Levente Szabo | 2012-05-18 14:56 | summary | Implement video sharing feature | New Feature - Implement video sharing feature
[10 empty] | Levente Szabo | 2012-05-18 14:59 | summary | New Feature - Implement video sharing feature | "New Feature" - Implement video sharing feature
[10 empty] | Levente Szabo | 2012-05-18 15:03 | summary | "New Feature" - Implement video sharing feature | Implement video sharing feature
[10 empty] | Levente Szabo | 2012-05-18 15:09 | summary | Implement video sharing feature | Video sharing feature
[10 empty] | Levente Szabo | 2012-05-23 13:03 | Story Points |  | 8
[10 empty] | Levente Szabo | 2012-07-14 14:20 | labels | IT&Dev | DEV IT
B4B-22 | Beem for Business | Video recording feature | Medium | Robert Mongose | To Do |  | 2012-05-17 12:52 | 2012-05-29 | 2012-06-02 | Levente Szabo | 2012-05-18 15:13 | summary | Implement video recording feature | Video recording feature
[10 empty] | Levente Szabo | 2012-05-18 16:31 | timeestimate |  | 0
[12 empty] | timespent |  | 115200
[12 empty] | WorklogId | 10204
[10 empty] | Levente Szabo | 2012-05-19 12:38 | Attachment |  | Components.docx
[10 empty] | Levente Szabo | 2012-05-19 12:43 | description | Create and test the video recording feature. (The main feature!!) | The video recording feature is the core feature of the MVP so we need to ensure that we deliver this in great quality and on time. {code:java} public int getFpsRate() { return stream.fpsRate; } {code}
[10 empty] | Levente Szabo | 2012-05-19 12:45 | summary | Video recording feature | Video recording feature xxx
[10 empty] | Levente Szabo | 2012-05-19 12:51 | description | The video recording feature is the core feature of the MVP so we need to ensure that we deliver this in great quality and on time. {code:java} public int getFpsRate() { return stream.fpsRate; } {code} | The video recording feature is the core feature of the MVP so we need to ensure that we deliver this in great quality and on time! Guys, for starters, make sure that when you call the FpsRate getter the stream isn't null, the feature will only work this way! If you have any questions pls turn immediately to me or [~robert], he is an expert on this. {code:java} public int getFpsRate() { return stream.fpsRate; } {code}
[10 empty] | Levente Szabo | 2012-05-19 12:53 | Attachment | Components.docx
[10 empty] | Levente Szabo | 2012-05-19 12:54 | Attachment |  | Video Streaming Architecture.docx
[10 empty] | Levente Szabo | 2012-05-19 12:54 | summary | Video recording feature xxx | Video recording feature
[10 empty] | Levente Szabo | 2012-05-19 12:56 | Attachment |  | Video streaming.jpg
[10 empty] | Levente Szabo | 2012-05-19 12:56 | Attachment | Video streaming.jpg
[10 empty] | Levente Szabo | 2012-05-19 12:56 | Attachment |  | Video streaming.psd.jpg
[10 empty] | Levente Szabo | 2012-05-19 12:56 | Attachment | Video streaming.psd.jpg
[10 empty] | Levente Szabo | 2012-05-19 12:58 | Attachment |  | Graphical requirements.docx
[10 empty] | Levente Szabo | 2012-05-19 13:04 | Attachment |  | Stream screen design.psd
[10 empty] | Levente Szabo | 2012-05-23 13:02 | Story Points |  | 4
[10 empty] | Levente Szabo | 2012-07-14 14:20 | labels | IT&Dev | DEV IT
B4B-21 | Beem for Business | Implement MVP functions | Medium | Levente Szabo | Done | Done | 2012-05-17 12:40 | 2012-05-10 | 2012-05-26 | Levente Szabo | 2012-05-17 12:42 | Start Date | 28/Jun/16 | 11/May/16
[10 empty] | Levente Szabo | 2012-05-17 12:42 | End Date | 12/Jul/16 | 27/Jul/16
[10 empty] | Levente Szabo | 2012-05-17 12:42 | End Date | 27/Jul/16 | 27/May/16
[10 empty] | Levente Szabo | 2012-05-17 13:28 | Sprint |  | Dev sprint
[10 empty] | Levente Szabo | 2012-05-17 13:28 | Rank |  | Ranked higher
[10 empty] | Levente Szabo | 2012-05-22 10:17 | labels | IT&Dev | IT&Dev billable
[10 empty] | Levente Szabo | 2012-05-22 10:19 | timeestimate |  | 0
[12 empty] | timespent |  | 432000
[12 empty] | WorklogId | 10401
[10 empty] | Levente Szabo | 2012-05-22 12:38 | issuetype | Task | Epic
[10 empty] | Levente Szabo | 2012-05-22 14:08 | timespent | 432000 | 506040
[12 empty] | WorklogId | 10401
[10 empty] | Levente Szabo | 2012-05-22 14:08 | timeestimate | 0 | 144000
[12 empty] | timespent | 506040 | 362040
[12 empty] | WorklogId | 10401
[10 empty] | Levente Szabo | 2012-05-22 14:09 | timeestimate | 144000 | 0
[12 empty] | timespent | 362040 | 506040
[12 empty] | WorklogId | 10403
[10 empty] | Levente Szabo | 2012-05-22 14:10 | WorklogId | 10403
[10 empty] | Levente Szabo | 2012-05-22 14:12 | timespent | 506040 | 524040
[12 empty] | WorklogId | 10403
[10 empty] | Levente Szabo | 2012-05-22 16:21 | WorklogId | 10403
[10 empty] | Levente Szabo | 2012-05-22 16:21 | WorklogId | 10401
[10 empty] | Levente Szabo | 2012-05-23 13:02 | Story Points |  | 4
[10 empty] | Levente Szabo | 2012-06-08 16:54 | assignee |  | Levente Szabo
[10 empty] | Levente Szabo | 2012-06-09 10:09 | resolution |  | Done
[12 empty] | status | To Do | Done
[10 empty] | Levente Szabo | 2012-07-14 14:20 | labels | IT&Dev billable | DEV IT
[10 empty] | Levente Szabo | 2012-08-11 14:57 | labels | DEV IT | DEV IT validation
[10 empty] | Levente Szabo | 2012-08-11 15:02 | labels | DEV IT validation | DEV IT
B4B-20 | Beem for Business | Log-in form | Medium | Robert Mongose | To Do |  | 2012-05-16 11:04 | 2012-05-24 | 2012-05-26 | Levente Szabo | 2012-05-16 11:04 | Start Date | 23/May/16 | 25/May/16
[10 empty] | Levente Szabo | 2012-05-16 11:04 | End Date | 25/May/16 | 27/May/16
[10 empty] | Levente Szabo | 2012-05-17 12:47 | Parent |  | B4B-21
[12 empty] | issuetype | Task | Sub-task
[10 empty] | Levente Szabo | 2012-05-18 15:08 | summary | Create log-in form | Log-in form
[10 empty] | Levente Szabo | 2012-05-23 13:02 | Story Points |  | 4
[10 empty] | Levente Szabo | 2012-07-14 14:20 | labels | IT&Dev | DEV IT
B4B-19 | Beem for Business | Sign-up form | Medium | Levente Szabo | In Progress |  | 2012-05-16 11:03 | 2012-05-22 | 2012-05-24 | Levente Szabo | 2012-05-16 11:03 | Link |  | This issue is blocked by B4B-9
[10 empty] | Levente Szabo | 2012-05-17 12:49 | Parent |  | B4B-21
[12 empty] | issuetype | Task | Sub-task
[10 empty] | Levente Szabo | 2012-05-18 15:11 | summary | Create reg form | Registration form
[10 empty] | Levente Szabo | 2012-05-18 16:31 | timeestimate |  | 0
[12 empty] | timespent |  | 57600
[12 empty] | WorklogId | 10205
[10 empty] | Levente Szabo | 2012-05-22 16:49 | assignee | Robert Mongose | Levente Szabo
[10 empty] | Levente Szabo | 2012-05-22 16:49 | summary | Registration form | Sign-up form
[10 empty] | Levente Szabo | 2012-05-23 13:02 | Story Points |  | 4
[10 empty] | Levente Szabo | 2012-07-13 16:17 | status | To Do | In Progress
[10 empty] | Levente Szabo | 2012-07-14 14:20 | labels | IT&Dev | DEV IT
B4B-18 | Beem for Business | Tutorial section | Medium | Dalia Lens | Done | Done | 2012-05-16 10:59 | 2012-05-16 | 2012-05-22 | Levente Szabo | 2012-05-17 12:50 | Parent |  | B4B-21
[12 empty] | issuetype | Task | Sub-task
[10 empty] | Levente Szabo | 2012-05-18 15:09 | assignee | Robert Mongose | Levente Szabo
[10 empty] | Levente Szabo | 2012-05-18 15:09 | summary | Implement and test "Intro section" | Tutorial section
[10 empty] | Levente Szabo | 2012-05-18 15:09 | assignee | Levente Szabo | Dalia Lens
[10 empty] | Levente Szabo | 2012-05-18 16:59 | timeestimate |  | 0
[12 empty] | timespent |  | 144000
[12 empty] | WorklogId | 10206
[10 empty] | Levente Szabo | 2012-05-22 14:46 | resolution |  | Done
[12 empty] | status | To Do | Done
[10 empty] | Levente Szabo | 2012-07-14 14:20 | labels | IT&Dev | DEV IT
[10 empty] | Levente Szabo | 2012-08-09 11:38 | Story Points |  | 14
B4B-17 | Beem for Business | Set up cloud hosting | Low | Robert Mongose | Done | Done | 2012-05-16 10:54 | 2012-05-15 | 2012-05-15 | Levente Szabo | 2012-05-16 11:01 | Start Date | 6/Jun/16 | 16/May/16
[10 empty] | Levente Szabo | 2012-05-16 11:01 | End Date | 6/Jun/16 | 16/May/16
[10 empty] | Levente Szabo | 2012-05-17 13:28 | Sprint |  | Dev sprint
[10 empty] | Levente Szabo | 2012-05-18 13:48 | priority | Medium | Low
[10 empty] | Levente Szabo | 2012-05-22 14:45 | resolution |  | Done
[12 empty] | status | To Do | Done
[10 empty] | Levente Szabo | 2012-07-14 14:20 | labels | IT&Dev | DEV IT
[10 empty] | Levente Szabo | 2012-08-09 11:39 | Story Points |  | 18
B4B-16 | Beem for Business | Set up Dev Environment | Medium | Robert Mongose | Done | Done | 2012-05-16 10:52 | 2012-05-11 | 2012-05-15 | Levente Szabo | 2012-05-16 11:01 | Start Date | 2/Jun/16 | 12/May/16
[10 empty] | Levente Szabo | 2012-05-16 11:01 | End Date | 6/Jun/16 | 16/May/16
[10 empty] | Levente Szabo | 2012-05-17 13:28 | Sprint |  | Dev sprint
[10 empty] | Levente Szabo | 2012-05-22 14:44 | resolution |  | Done
[12 empty] | status | To Do | Done
[10 empty] | Levente Szabo | 2012-07-14 14:20 | labels | IT&Dev | DEV IT
[10 empty] | Levente Szabo | 2012-08-09 11:39 | Story Points |  | 8
B4B-15 | Beem for Business | Set up DB | Medium | Robert Mongose | Done | Done | 2012-05-16 10:51 | 2012-05-10 | 2012-05-10 | Levente Szabo | 2012-05-16 11:00 | Start Date | 1/Jun/16 | 11/May/16
[10 empty] | Levente Szabo | 2012-05-16 11:00 | End Date | 1/Jun/16 | 11/May/16
[10 empty] | Levente Szabo | 2012-05-17 13:28 | Sprint |  | Dev sprint
[10 empty] | Levente Szabo | 2012-05-22 14:44 | resolution |  | Done
[12 empty] | status | To Do | Done
[10 empty] | Levente Szabo | 2012-07-14 14:20 | labels | IT&Dev | DEV IT
[10 empty] | Levente Szabo | 2012-08-09 11:40 | Story Points |  | 4
B4B-14 | Beem for Business | Create landing page | Medium | Dalia Lens | To Do |  | 2012-05-14 21:41 | 2012-06-20 | 2012-06-22 | Levente Szabo | 2012-05-14 21:41 | Link |  | This issue is blocked by B4B-13
[10 empty] | Levente Szabo | 2012-05-14 22:00 | description | Based on design and copy version testing create final landing page for the service. | Based on design and copy version testing create final landing page for the service, optimized for conversion and social sharing.
[10 empty] | Levente Szabo | 2012-05-17 13:04 | summary | Create landing apge | Create landing page
[10 empty] | Levente Szabo | 2012-05-17 13:27 | Sprint |  | UX&UI sprint 2
[10 empty] | Levente Szabo | 2012-05-23 13:02 | Story Points |  | 6
[10 empty] | Levente Szabo | 2012-08-11 14:58 | labels | web | validation web
B4B-13 | Beem for Business | Decision on landing page design | Medium | Dalia Lens | In Progress |  | 2012-05-14 21:36 | 2012-06-19 | 2012-06-19 | Levente Szabo | 2012-05-14 21:36 | Link |  | This issue is blocked by B4B-12
[10 empty] | Levente Szabo | 2012-05-14 21:41 | Link |  | This issue blocks B4B-14
[10 empty] | Levente Szabo | 2012-05-14 21:42 | labels |  | web
[10 empty] | Levente Szabo | 2012-05-17 13:27 | Sprint |  | UX&UI sprint 2
[10 empty] | Levente Szabo | 2012-05-23 13:02 | Story Points |  | 6
[10 empty] | Levente Szabo | 2012-06-05 09:53 | summary | Decide on Landing page | Decision on Landing page
[10 empty] | Levente Szabo | 2012-06-05 09:53 | summary | Decision on Landing page | Decision on Landing page design
[10 empty] | Levente Szabo | 2012-06-05 09:53 | summary | Decision on Landing page design | Decision on landing page design
[10 empty] | Levente Szabo | 2012-06-05 10:03 | description | Based on Unbounce testing make decision on landing page design. | This is an All-Hands decision so all team members are welcome to weigh in with their opinion in the comment section. Please share your view in the comments so we can have everyone's opinion in one place. By the decision time we will have had many debates, A/B tests and some UX tests run so we should have enough data to work with.
[10 empty] | Levente Szabo | 2012-06-05 10:03 | status | To Do | In Progress
[10 empty] | Levente Szabo | 2012-06-05 10:03 | Component |  | Landing Page
[10 empty] | Levente Szabo | 2012-06-05 10:05 | description | This is an All-Hands decision so all team members are welcome to weigh in with their opinion in the comment section. Please share your view in the comments so we can have everyone's opinion in one place. By the decision time we will have had many debates, A/B tests and some UX tests run so we should have enough data to work with. | This is an All-Hands decision so all team members are welcome to weigh in with their opinion in the comment section. Please share your view in the comments on all components, namely the copy, the design, the timing, the highlighted features, so we can have everyone's opinion in one place. By the decision time we will have had many debates, A/B tests and some UX tests run so we should have enough data to work with.
[10 empty] | Levente Szabo | 2012-06-05 10:09 | Attachment |  | Graphical requirements.docx
[10 empty] | Levente Szabo | 2012-06-05 10:10 | Attachment |  | landingpage1.png
[10 empty] | Levente Szabo | 2012-06-05 10:11 | description | This is an All-Hands decision so all team members are welcome to weigh in with their opinion in the comment section. Please share your view in the comments on all components, namely the copy, the design, the timing, the highlighted features, so we can have everyone's opinion in one place. By the decision time we will have had many debates, A/B tests and some UX tests run so we should have enough data to work with. | This is an *All-Hands decision* so all team members are welcome to weigh in with their opinion in the comment section. Please share your view in the comments on all components, namely the copy, the design, the timing, the highlighted features, so we can have everyone's opinion in one place. By the decision time we will have had many debates, A/B tests and some UX tests run so we should have enough data to work with.
[10 empty] | Levente Szabo | 2012-06-05 10:35 | description | This is an *All-Hands decision* so all team members are welcome to weigh in with their opinion in the comment section. Please share your view in the comments on all components, namely the copy, the design, the timing, the highlighted features, so we can have everyone's opinion in one place. By the decision time we will have had many debates, A/B tests and some UX tests run so we should have enough data to work with. | This is an *All-Hands decision* so all team members are welcome to weigh in with their opinion in the comment section. Please share your view in the comments {color:red}on all components{color}, namely the copy, the design, the timing, the highlighted features, so we can have everyone's opinion in one place. By the decision time we will have had many debates, A/B tests and some UX tests run so we should have enough data to work with.
B4B-12 | Beem for Business | A/B test landing page | Low | Dalia Lens | In Progress |  | 2012-05-14 19:50 | 2012-06-05 | 2012-06-19 | Levente Szabo | 2012-05-14 19:50 | Link |  | This issue is blocked by B4B-11
[10 empty] | Levente Szabo | 2012-05-14 19:50 | labels |  | web
[10 empty] | Levente Szabo | 2012-05-14 21:36 | Link |  | This issue blocks B4B-13
[10 empty] | Levente Szabo | 2012-05-17 13:27 | Sprint |  | UX&UI sprint 2
[10 empty] | Levente Szabo | 2012-05-18 13:43 | priority | Medium | Low
[10 empty] | Levente Szabo | 2012-05-23 13:03 | Story Points |  | 8
[10 empty] | Levente Szabo | 2012-07-13 16:17 | status | To Do | In Progress
B4B-11 | Beem for Business | Landing page copy | Medium | Dalia Lens | In Progress |  | 2012-05-14 19:47 | 2012-05-31 | 2012-06-02 | Levente Szabo | 2012-05-14 19:48 | assignee |  | Dalia Lens
[10 empty] | Levente Szabo | 2012-05-14 19:48 | labels |  | web
[10 empty] | Levente Szabo | 2012-05-14 19:50 | Link |  | This issue blocks B4B-12
[10 empty] | Levente Szabo | 2012-05-17 13:27 | Sprint |  | UX&UI sprint 2
[10 empty] | Levente Szabo | 2012-05-22 10:20 | timeestimate |  | 0
[12 empty] | timespent |  | 57600
[12 empty] | WorklogId | 10402
[10 empty] | Levente Szabo | 2012-05-22 10:21 | labels | web | billable web
[10 empty] | Levente Szabo | 2012-05-23 13:02 | Story Points |  | 6
[10 empty] | Levente Szabo | 2012-07-13 16:17 | status | To Do | In Progress
[10 empty] | Levente Szabo | 2012-08-11 14:58 | labels | billable web | billable validation web
B4B-10 | Beem for Business | Design Feedback (3.) | Medium | Dalia Lens | To Do |  | 2012-05-14 19:42 | 2012-05-23 | 2012-05-23 | Levente Szabo | 2012-05-14 19:42 | Link |  | This issue blocks B4B-9
[10 empty] | Levente Szabo | 2012-05-17 13:26 | Sprint |  | UX&UI sprint
[10 empty] | Levente Szabo | 2012-05-23 13:01 | Story Points |  | 2
[10 empty] | Levente Szabo | 2012-07-14 14:21 | labels | UI&UX | user-experience user-interface
B4B-9 | Beem for Business | Design Feedback (2.) | Medium | Dalia Lens | Done | Done | 2012-05-14 19:36 | 2012-05-16 | 2012-05-16 | Levente Szabo | 2012-05-14 19:37 | labels |  | UI&UX
[10 empty] | Levente Szabo | 2012-05-14 19:42 | Link |  | This issue is blocked by B4B-10
[10 empty] | Levente Szabo | 2012-05-16 11:03 | Link |  | This issue blocks B4B-19
[10 empty] | Levente Szabo | 2012-05-17 13:26 | Sprint |  | UX&UI sprint
[10 empty] | Levente Szabo | 2012-05-17 13:26 | Rank |  | Ranked higher
[10 empty] | Levente Szabo | 2012-05-17 13:26 | Rank |  | Ranked lower
[10 empty] | Levente Szabo | 2012-05-22 14:45 | resolution |  | Done
[12 empty] | status | To Do | Done
[10 empty] | Levente Szabo | 2012-05-22 14:59 | resolution | Done
[12 empty] | status | Done | To Do
[10 empty] | Levente Szabo | 2012-05-23 13:02 | Story Points |  | 4
[10 empty] | Levente Szabo | 2012-07-13 18:02 | resolution |  | Done
[12 empty] | status | To Do | Done
[10 empty] | Levente Szabo | 2012-07-14 14:21 | labels | UI&UX | user-experience user-interface
B4B-8 | Beem for Business | Design Feedback (1.) | Medium | Dalia Lens | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Levente Szabo | 2012-05-14 19:29 | Link |  | This issue relates to B4B-7
[10 empty] | Levente Szabo | 2012-05-14 19:37 | labels |  | UI&UX
[10 empty] | Levente Szabo | 2012-05-17 13:26 | Sprint |  | UX&UI sprint
[10 empty] | Levente Szabo | 2012-05-17 13:33 | Attachment |  | landingpage1.png
[12 empty] | Attachment |  | landingpage2.jpg
[10 empty] | Levente Szabo | 2012-05-17 13:34 | Component |  | Landing Page
[10 empty] | Levente Szabo | 2012-05-17 13:36 | Attachment | landingpage2.jpg
[10 empty] | Levente Szabo | 2012-05-17 13:36 | Attachment | landingpage1.png
[10 empty] | Levente Szabo | 2012-05-17 13:37 | Attachment |  | landingpage1.png
[12 empty] | Attachment |  | landingpage2.jpg
[10 empty] | Levente Szabo | 2012-05-17 13:37 | Attachment | landingpage1.png
[10 empty] | Levente Szabo | 2012-05-17 14:16 | Attachment |  | landingpage1.png
[10 empty] | Levente Szabo | 2012-05-17 14:17 | Attachment | landingpage1.png
[10 empty] | Levente Szabo | 2012-05-17 15:30 | Attachment |  | Components.txt
[12 empty] | Attachment |  | Meeting minutes - Graphic design feedback(1).docx
[10 empty] | Levente Szabo | 2012-05-17 16:02 | description | Feedback to the first design mockup from designers. Give follow-up briefing if needed (most probably needed) | _To be present: UI project team lead, product manager, designers_ During the meeting with the designer team, we need to cover the following: * Make sure they understood the business concept * Feedback to the first design mockup from designers. Give follow-up briefing if needed (most probably needed)
[10 empty] | Levente Szabo | 2012-05-17 16:03 | description | _To be present: UI project team lead, product manager, designers_ During the meeting with the designer team, we need to cover the following: * Make sure they understood the business concept * Feedback to the first design mockup from designers. Give follow-up briefing if needed (most probably needed) | __To be present: UI project team lead, product manager, designers. Please come prepared!_ During the meeting with the designer team, we need to cover the following: * Make sure they understood the business concept * Feedback to the first design mockup from designers. Give follow-up briefing if needed (most probably needed)
[10 empty] | Levente Szabo | 2012-05-17 16:03 | description | __To be present: UI project team lead, product manager, designers. Please come prepared!_ During the meeting with the designer team, we need to cover the following: * Make sure they understood the business concept * Feedback to the first design mockup from designers. Give follow-up briefing if needed (most probably needed) | To be present: UI project team lead, product manager, designers. Please come prepared!_ During the meeting with the designer team, we need to cover the following: * Make sure they understood the business concept * Feedback to the first design mockup from designers. Give follow-up briefing if needed (most probably needed)
[10 empty] | Levente Szabo | 2012-05-17 16:03 | description | To be present: UI project team lead, product manager, designers. Please come prepared!_ During the meeting with the designer team, we need to cover the following: * Make sure they understood the business concept * Feedback to the first design mockup from designers. Give follow-up briefing if needed (most probably needed) | _To be present: UI project team lead, product manager, designers. Please come prepared!_ During the meeting with the designer team, we need to cover the following: * Make sure they understood the business concept * Feedback to the first design mockup from designers. Give follow-up briefing if needed (most probably needed)
[10 empty] | Levente Szabo | 2012-05-17 16:06 | description | _To be present: UI project team lead, product manager, designers. Please come prepared!_ During the meeting with the designer team, we need to cover the following: * Make sure they understood the business concept * Feedback to the first design mockup from designers. Give follow-up briefing if needed (most probably needed) | _To be present: UI project team lead, product manager, designers. Please come prepared!_ *First design feedback meeting* During the meeting with the designer team, we need to cover the following: * Make sure they understood the business concept * Feedback to the first design mockup. Give follow-up briefing if needed (most probably needed) * Request corrective actions and/or clear out all remaining concerns
[10 empty] | Levente Szabo | 2012-05-17 16:06 | description | _To be present: UI project team lead, product manager, designers. Please come prepared!_ *First design feedback meeting* During the meeting with the designer team, we need to cover the following: * Make sure they understood the business concept * Feedback to the first design mockup. Give follow-up briefing if needed (most probably needed) * Request corrective actions and/or clear out all remaining concerns | _To be present: UI project team lead, product manager, designers. Please come prepared!_ *First design feedback meeting* During the meeting with the designer team, we need to cover the following: * Make sure they understood the business concept * Feedback to the first design mockup. {color:red}Give follow-up briefing if needed{color} (most probably needed) * Request corrective actions and/or clear out all remaining concerns
[10 empty] | Levente Szabo | 2012-05-17 16:07 | description | _To be present: UI project team lead, product manager, designers. Please come prepared!_ *First design feedback meeting* During the meeting with the designer team, we need to cover the following: * Make sure they understood the business concept * Feedback to the first design mockup. {color:red}Give follow-up briefing if needed{color} (most probably needed) * Request corrective actions and/or clear out all remaining concerns | _To be present: UI project team lead, product manager, designers. Please come prepared!_(i) *First design feedback meeting* During the meeting with the designer team, we need to cover the following: * Make sure they understood the business concept * Feedback to the first design mockup. {color:red}Give follow-up briefing if needed{color} (most probably needed:)) * Request corrective actions and/or clear out all remaining concerns
[10 empty] | Levente Szabo | 2012-05-17 16:08 | description | _To be present: UI project team lead, product manager, designers. Please come prepared!_(i) *First design feedback meeting* During the meeting with the designer team, we need to cover the following: * Make sure they understood the business concept * Feedback to the first design mockup. {color:red}Give follow-up briefing if needed{color} (most probably needed:)) * Request corrective actions and/or clear out all remaining concerns | _To be present: UI project team lead, product manager, designers. Please come prepared!_(i) +*First design feedback meeting*+ During the meeting with the designer team, we need to cover the following: * Make sure they understood the business concept * Feedback to the first design mockup. {color:red}Give follow-up briefing if needed{color} (most probably needed:)) * Request corrective actions and/or clear out all remaining concerns
[10 empty] | Levente Szabo | 2012-05-17 16:26 | Attachment | Meeting minutes - Graphic design feedback(1).docx
[10 empty] | Levente Szabo | 2012-05-17 16:26 | Attachment |  | Meeting minutes.docx
[10 empty] | Levente Szabo | 2012-05-17 17:37 | labels | UI&UX | UI UX
[10 empty] | Levente Szabo | 2012-05-17 17:37 | Component |  | Grid
[10 empty] | Levente Szabo | 2012-05-18 12:20 | Link |  | This issue relates to B4B-6
[10 empty] | Levente Szabo | 2012-05-18 17:55 | Component |  | Android App
[12 empty] | Component |  | iOS App
[12 empty] | Component | Grid
[10 empty] | Levente Szabo | 2012-05-18 17:56 | labels | UI UX | UI UX interactions
[10 empty] | Levente Szabo | 2012-05-18 17:57 | labels | UI UX interactions | UI UX interactions user-experience user-inteface
[10 empty] | Levente Szabo | 2012-05-18 17:58 | labels | UI UX interactions user-experience user-inteface | interactions user-experience user-inteface
[10 empty] | Levente Szabo | 2012-05-18 17:58 | labels | interactions user-experience user-inteface | interactions user-experience user-interface
[10 empty] | Levente Szabo | 2012-05-18 17:59 | Link |  | This issue is blocked by B4B-7
[10 empty] | Levente Szabo | 2012-05-18 17:59 | Link | This issue relates to B4B-7
[10 empty] | Levente Szabo | 2012-05-18 17:59 | Link |  | This issue relates to B4B-4
[10 empty] | Levente Szabo | 2012-05-18 18:02 | description | _To be present: UI project team lead, product manager, designers. Please come prepared!_(i) +*First design feedback meeting*+ During the meeting with the designer team, we need to cover the following: * Make sure they understood the business concept * Feedback to the first design mockup. {color:red}Give follow-up briefing if needed{color} (most probably needed:)) * Request corrective actions and/or clear out all remaining concerns | _To be present: UI project team lead, product manager, designers. Please come prepared!_ (on) +*First design feedback meeting*+ During the meeting with the designer team, we need to cover the following: * Make sure they understood the business concept * Feedback to the first design mockup. {color:red}Give follow-up briefing if needed{color} (most probably needed:)) * Request corrective actions and/or clear out all remaining concerns
[10 empty] | Levente Szabo | 2012-05-18 18:02 | description | _To be present: UI project team lead, product manager, designers. Please come prepared!_ (on) +*First design feedback meeting*+ During the meeting with the designer team, we need to cover the following: * Make sure they understood the business concept * Feedback to the first design mockup. {color:red}Give follow-up briefing if needed{color} (most probably needed:)) * Request corrective actions and/or clear out all remaining concerns | _To be present: UI project team lead, product manager, designers. Please come prepared!_ (on) +*First design feedback meeting*+ During the meeting with the designer team, we need to cover the following: * Make sure they understood the business concept * Feedback to the first design mockup. {color:red}Give follow-up briefing if needed{color} (most probably needed :)) * Request corrective actions and/or clear out all remaining concerns
[10 empty] | Levente Szabo | 2012-05-19 11:29 | Attachment | Components.txt
[10 empty] | Levente Szabo | 2012-05-19 11:29 | Attachment |  | Screen mockups.psd
[10 empty] | Levente Szabo | 2012-05-19 11:32 | Attachment | landingpage2.jpg
[10 empty] | Levente Szabo | 2012-05-19 11:32 | Attachment |  | mockups-login.jpg
[10 empty] | Levente Szabo | 2012-05-19 11:33 | Attachment | mockups-login.jpg
[10 empty] | Levente Szabo | 2012-05-19 11:33 | Attachment |  | mockups-login.jpg
[10 empty] | Levente Szabo | 2012-05-19 11:42 | timeestimate |  | 0
[12 empty] | timespent |  | 5400
[12 empty] | WorklogId | 10207
[10 empty] | Levente Szabo | 2012-05-19 11:44 | timespent | 5400 | 7200
[12 empty] | WorklogId | 10208
[10 empty] | Levente Szabo | 2012-05-19 11:51 | Attachment |  | landingpage2.jpg
[10 empty] | Levente Szabo | 2012-05-19 11:52 | Attachment | landingpage2.jpg
[10 empty] | Levente Szabo | 2012-05-19 11:53 | Attachment | mockups-login.jpg
[10 empty] | Levente Szabo | 2012-05-19 11:53 | Attachment |  | mockups-login.jpg
[10 empty] | Levente Szabo | 2012-05-19 11:59 | Attachment | mockups-login.jpg
[10 empty] | Levente Szabo | 2012-05-19 11:59 | Attachment |  | mockups-login.jpg
[10 empty] | Levente Szabo | 2012-05-19 17:31 | Attachment | mockups-login.jpg
[10 empty] | Levente Szabo | 2012-05-19 17:32 | Attachment |  | mockups-login2.jpg
[10 empty] | Levente Szabo | 2012-05-19 22:30 | Attachment | mockups-login2.jpg
[10 empty] | Levente Szabo | 2012-05-19 22:31 | Attachment |  | mockups-login.jpg
[10 empty] | Levente Szabo | 2012-05-22 09:53 | Attachment | mockups-login.jpg
[10 empty] | Levente Szabo | 2012-05-22 09:53 | Attachment |  | login (1).jpg
[10 empty] | Levente Szabo | 2012-05-22 14:35 | resolution |  | Done
[12 empty] | status | To Do | Done
B4B-7 | Beem for Business | Graphic designer briefing (1.) | High | Dalia Lens | Done | Done | 2012-05-14 19:18 | 2012-06-02 | 2012-06-02 | Levente Szabo | 2012-05-14 19:18 | Link |  | This issue is blocked by B4B-6
[10 empty] | Levente Szabo | 2012-05-14 19:19 | End Date | 6/May/16 | 1/Jun/16
[10 empty] | Levente Szabo | 2012-05-14 19:21 | Start Date | 1/Jun/16 | 3/Jun/16
[10 empty] | Levente Szabo | 2012-05-14 19:21 | End Date | 1/Jun/16 | 3/Jun/16
[10 empty] | Levente Szabo | 2012-05-14 19:29 | Link |  | This issue relates to B4B-8
[10 empty] | Levente Szabo | 2012-05-14 19:37 | labels |  | UI&UX
[10 empty] | Levente Szabo | 2012-05-17 13:25 | Sprint |  | BVP Sprint 2
[10 empty] | Levente Szabo | 2012-05-18 16:24 | timeestimate |  | 0
[12 empty] | timespent |  | 5400
[12 empty] | WorklogId | 10201
[10 empty] | Levente Szabo | 2012-05-18 17:59 | Link |  | This issue blocks B4B-8
[10 empty] | Levente Szabo | 2012-05-18 17:59 | Link | This issue relates to B4B-8
[10 empty] | Levente Szabo | 2012-05-22 14:41 | resolution |  | Done
[12 empty] | status | To Do | Done
[10 empty] | Levente Szabo | 2012-07-14 14:21 | labels | UI&UX | user-experience user-interface
B4B-6 | Beem for Business | MVP functionality | High | Owen Klyed | Done | Done | 2012-05-14 18:50 | 2012-05-31 | 2012-06-02 | Levente Szabo | 2012-05-14 18:50 | Link |  | This issue is blocked by B4B-5
[10 empty] | Levente Szabo | 2012-05-14 18:50 | labels |  | validation
[10 empty] | Levente Szabo | 2012-05-14 19:18 | Link |  | This issue blocks B4B-7
[10 empty] | Levente Szabo | 2012-05-14 19:20 | Start Date |  | 1/Jun/16
[10 empty] | Levente Szabo | 2012-05-14 19:20 | End Date |  | 3/Jun/16
[10 empty] | Levente Szabo | 2012-05-17 13:25 | Sprint |  | BVP Sprint 1
[10 empty] | Levente Szabo | 2012-05-18 12:20 | Link |  | This issue relates to B4B-8
[10 empty] | Levente Szabo | 2012-05-18 16:07 | timeestimate |  | 0
[12 empty] | timespent |  | 43200
[12 empty] | WorklogId | 10200
[10 empty] | Levente Szabo | 2012-05-19 13:43 | status | To Do | In Progress
[10 empty] | Levente Szabo | 2012-05-22 14:41 | resolution |  | Done
[12 empty] | status | In Progress | Done
[10 empty] | Levente Szabo | 2012-08-09 11:41 | Story Points |  | 6
[10 empty] | Levente Szabo | 2012-08-11 14:58 | labels | validation
[10 empty] | Levente Szabo | 2012-08-11 15:02 | labels |  | validation
B4B-5 | Beem for Business | Traditional market research | Lowest | Owen Klyed | Done | Done | 2012-05-14 18:48 | 2012-05-16 | 2012-05-30 | Levente Szabo | 2012-05-14 18:48 | Link |  | This issue relates to B4B-3
[10 empty] | Levente Szabo | 2012-05-14 18:50 | Link |  | This issue blocks B4B-6
[10 empty] | Levente Szabo | 2012-05-14 18:51 | labels |  | validation
[10 empty] | Levente Szabo | 2012-05-14 19:23 | Start Date |  | 17/May/16
[10 empty] | Levente Szabo | 2012-05-14 19:24 | End Date |  | 31/May/16
[10 empty] | Levente Szabo | 2012-05-17 13:25 | Sprint |  | BVP Sprint 1
[10 empty] | Levente Szabo | 2012-05-17 13:25 | Rank |  | Ranked higher
[10 empty] | Levente Szabo | 2012-05-18 13:24 | status | To Do | In Progress
[10 empty] | Levente Szabo | 2012-05-18 13:42 | priority | Medium | Low
[10 empty] | Levente Szabo | 2012-05-18 13:43 | priority | Low | Lowest
[10 empty] | Levente Szabo | 2012-05-18 14:44 | resolution |  | Done
[12 empty] | status | In Progress | Done
[10 empty] | Levente Szabo | 2012-05-19 13:45 | resolution | Done
[12 empty] | status | Done | In Progress
[10 empty] | Levente Szabo | 2012-05-22 15:01 | resolution |  | Done
[12 empty] | status | In Progress | Done
[10 empty] | Levente Szabo | 2012-05-24 14:33 | timeestimate |  | 0
[12 empty] | timespent |  | 288000
[12 empty] | WorklogId | 10404
[10 empty] | Levente Szabo | 2012-08-09 11:41 | Story Points |  | 22
B4B-4 | Beem for Business | Validation landing page | Highest | Owen Klyed | Done | Done | 2012-05-14 18:44 | 2012-05-17 | 2012-05-17 | Levente Szabo | 2012-05-14 18:44 | Link |  | This issue is blocked by B4B-3
[10 empty] | Levente Szabo | 2012-05-14 19:22 | Start Date |  | 18/May/16
[10 empty] | Levente Szabo | 2012-05-14 19:22 | End Date |  | 18/May/16
[10 empty] | Levente Szabo | 2012-05-17 13:24 | Sprint |  | BVP Sprint 1
[10 empty] | Levente Szabo | 2012-05-18 13:43 | priority | High | Highest
[10 empty] | Levente Szabo | 2012-05-18 14:44 | status | To Do | In Progress
[10 empty] | Levente Szabo | 2012-05-18 14:47 | resolution |  | Done
[12 empty] | status | In Progress | Done
[10 empty] | Levente Szabo | 2012-05-18 17:59 | Link |  | This issue relates to B4B-8
[10 empty] | Levente Szabo | 2012-05-22 14:36 | status | Done | Done
[10 empty] | Levente Szabo | 2012-05-22 14:46 | resolution | Done
[12 empty] | status | Done | To Do
[10 empty] | Levente Szabo | 2012-05-22 15:00 | resolution |  | Done
[12 empty] | status | To Do | Done
[10 empty] | Levente Szabo | 2012-05-22 15:01 | resolution | Done
[12 empty] | status | Done | In Progress
[10 empty] | Levente Szabo | 2012-05-23 10:19 | Fix Version |  | 1.0
[10 empty] | Levente Szabo | 2012-05-23 13:01 | Story Points |  | 2
[10 empty] | Levente Szabo | 2012-05-24 14:22 | resolution |  | Done
[12 empty] | status | In Progress | Done
[10 empty] | Levente Szabo | 2012-05-24 14:33 | timeestimate |  | 0
[12 empty] | timespent |  | 28800
[12 empty] | WorklogId | 10405
B4B-3 | Beem for Business | Customer interviews | Highest | Owen Klyed | Done | Done | 2012-05-14 18:40 | 2012-05-16 | 2012-05-30 | Levente Szabo | 2012-05-14 18:41 | summary | Conduct 50 customer interviews | Customer interviews
[10 empty] | Levente Szabo | 2012-05-14 18:44 | Link |  | This issue blocks B4B-4
[10 empty] | Levente Szabo | 2012-05-14 18:45 | labels |  | validation
[10 empty] | Levente Szabo | 2012-05-14 18:48 | Link |  | This issue relates to B4B-5
[10 empty] | Levente Szabo | 2012-05-14 18:57 | assignee |  | Owen Klyed
[10 empty] | Levente Szabo | 2012-05-14 19:01 | Start Date |  | 17/May/16
[10 empty] | Levente Szabo | 2012-05-14 19:02 | End Date |  | 31/May/16
[10 empty] | Levente Szabo | 2012-05-14 19:24 | Story Points |  | 72
[10 empty] | Levente Szabo | 2012-05-14 22:14 | timeestimate |  | 0
[12 empty] | timespent |  | 14400
[12 empty] | WorklogId | 10100
[10 empty] | Levente Szabo | 2012-05-17 13:24 | Sprint |  | BVP Sprint 1
[10 empty] | Levente Szabo | 2012-05-18 13:24 | status | To Do | In Progress
[10 empty] | Levente Szabo | 2012-05-19 16:04 | resolution |  | Done
[12 empty] | status | In Progress | Done
B4B-1 | Beem for Business | Secure and buy the domain name | Low | Dalia Lens | Done | Done | 2012-05-11 11:50 | 2012-05-16 | 2012-05-16 | Levente Szabo | 2012-05-11 11:55 | description |  | We need to make sure that we have the domain name rights and all social media accounts.
[12 empty] | priority | Medium | High
[12 empty] | Sprint |  | LS Sprint 1
[12 empty] | labels |  | web
[10 empty] | Levente Szabo | 2012-05-11 12:53 | Story Points |  | 4
[10 empty] | Levente Szabo | 2012-05-14 18:52 | Sprint | LS Sprint 1
[10 empty] | Levente Szabo | 2012-05-14 18:57 | assignee |  | Dalia Lens
[10 empty] | Levente Szabo | 2012-05-14 19:05 | Start Date |  | 17/May/16
[10 empty] | Levente Szabo | 2012-05-14 19:06 | End Date |  | 17/May/16
[10 empty] | Levente Szabo | 2012-05-17 13:28 | Sprint |  | Dev sprint
[10 empty] | Levente Szabo | 2012-05-17 13:28 | Rank |  | Ranked lower
[10 empty] | Levente Szabo | 2012-05-17 13:28 | Rank |  | Ranked higher
[10 empty] | Levente Szabo | 2012-05-18 13:48 | priority | High | Low
[10 empty] | Levente Szabo | 2012-05-22 14:45 | resolution |  | Done
[12 empty] | status | To Do | Done
40