## Issue Navigator
Project | Key | Summary | P | Assignee | Status | Resolution | Created | Start Date | End Date | Comment Author | Comment Time | Comment
Beem for Business | B4B-58 | Website layout | Medium | Dalia Lens | To Do |  | 2012-07-21 13:53 | 2012-05-18 | 2012-05-23 | Levente Szabo | 2012-08-14 11:37 | [~dalia], can you ask for some more specific instructions from the customer? What they gave us so far is pretty hazy...
[10 empty] | Levente Szabo | 2012-08-14 11:38 | Oh, never mind, I found the attachement with the instructions! Sorry! (y)
Beem for Business | B4B-57 | Second mockup | Medium | Dalia Lens | To Do |  | 2012-07-21 13:52 | 2012-05-14 | 2012-05-18 | Dalia Lens | 2012-05-15 | The last version is really looking good my friend!!
Beem for Business | B4B-56 | First mockup | Medium | Dalia Lens | To Do |  | 2012-07-21 13:52 | 2012-05-10 | 2012-05-14 | Wilbert Dawkins | 2012-05-14 | I checked the first version and I have a feeling that *this is not the direction the cusstomer had in mind*…Let’s talk asap.
Beem for Business | B4B-55 | Brand color scheme | Medium | Dalia Lens | To Do |  | 2012-07-21 13:51 | 2012-05-08 | 2012-05-10 |  | 2012-05-10
Beem for Business | B4B-49 | Beem Inc. - Company website design | Highest | Dalia Lens | Done | Done | 2012-07-13 17:11 | 2012-05-08 | 2012-05-23 | Levente Szabo | 2012-07-18 16:57 | Do we already have the signed contract?
[10 empty] | Casey Ford | 2012-07-18 16:57 | Yep! They signed yesterday!
[10 empty] | Levente Szabo | 2012-07-20 13:39 | Thanks, this is awesome! I've been looking forward to this project!
Beem for Business | B4B-38 | Historical analysis | Low | Dalia Lens | Done | Done | 2012-05-19 13:44 | 2012-05-22 | 2012-05-30 | Owen Klyed | 2012-06-09 10:58 | Re-send the invoice to customer, pls
[10 empty] | Owen Klyed | 2012-06-09 10:58 | Just talked to them, they are having difficulties wit their AP system, should be up and running by EOB today.
Beem for Business | B4B-37 | Online research | Low | Owen Klyed | Done | Done | 2012-05-19 13:44 | 2012-05-16 | 2012-05-22 | Levente Szabo | 2012-05-22 | OK everyone, I have created the final list with survey participants. Please find it as an attachement and have at it!
Beem for Business | B4B-36 | Phone interviews | Medium | Owen Klyed | Done | Done | 2012-05-19 13:38 | 2012-05-25 | 2012-05-30 | Levente Szabo | 2012-05-30 | Similarly to the online research, list has been posted! *Get down to the phones and start working* your way down the list.
Beem for Business | B4B-35 | In person interviews | Medium | Owen Klyed | Done | Done | 2012-05-19 13:36 | 2012-05-16 | 2012-05-26 | Levente Szabo | 2012-05-26 | Participant list has been generated for the survey. *Please schedule time* with me for a short review after your customer interviews.
Beem for Business | B4B-34 | Clarify color schemes | Medium | Casey Ford | In Progress |  | 2012-05-19 11:39 | 2012-05-16 | 2012-05-22 | Casey Ford | 2012-06-14 | [~dalia], make sure you review the instruction doc I sent you earlier! That has a lot of added info to this task.
Beem for Business | B4B-33 | Feedback on components | Medium | Dalia Lens | To Do |  | 2012-05-17 15:26 | 2012-05-25 | 2012-05-30 | Casey Ford | 2012-05-29 | Review meeting has been rescheduled!!! Make sure you don't forget and show up when you're supposed to.
Beem for Business | B4B-32 | Feedback on overall design approach | Medium | Owen Klyed | Done | Done | 2012-05-17 15:25 | 2012-05-16 | 2012-05-26 | Dalia Lens | 2012-06-20 | I think this should be rescheduled, since 3 of the lead designers bailed from today's meeting. Thoughts?
Beem for Business | B4B-31 | Collect feedback | Low | Casey Ford | To Do |  | 2012-05-17 13:07 | 2012-06-14 | 2012-06-14 | Casey Ford | 2012-06-14 | Today's presentation went really well! Learned a ton from those customer feedbacks.
Beem for Business | B4B-30 | Set up FB group for beta testers | Medium | Casey Ford | To Do |  | 2012-05-17 13:06 | 2012-05-29 | 2012-05-29 | Levente Szabo | 2012-05-29 | Have you seen this group? Members are pouring in the comments
Beem for Business | B4B-29 | Plan the email campaigns | Medium | Levente Szabo | Done | Done | 2012-05-17 13:02 | 2012-06-13 | 2012-06-20 |  | 2012-06-20 | I wanna see the following things in place before we get started: * Email campaign created in Mailchimp * Relevant list of target customers ** Filtered by how long they are customers and how much they have spent so far * Email copy ** 2 versions for early A/B testing
Beem for Business | B4B-28 | Copy for email campaigns | Low | Casey Ford | To Do |  | 2012-05-17 13:01 | 2012-06-13 | 2012-06-20 | Owen Klyed | 2012-06-08 11:35 | Not bad in terms of copy. Can we grab a coffee today and discuss your ideas?
[10 empty] | Levente Szabo | 2012-06-08 11:47 | Would love to. Ping me anytime.
Beem for Business | B4B-27 | Set up Mailchimp | Low | Casey Ford | In Progress |  | 2012-05-17 12:58 | 2012-06-12 | 2012-06-12
Beem for Business | B4B-26 | Set up Hootsuite account | Medium | Casey Ford | To Do |  | 2012-05-17 12:57 | 2012-06-12 | 2012-06-12 | Robert Mongose |  | Who will be managing the social media accounts exactly? *I want names! :)*
Beem for Business | B4B-25 | "React" feature | Medium | Dalia Lens | To Do |  | 2012-05-17 12:55 | 2012-06-09 | 2012-06-13 | Owen Klyed | 2012-06-08 16:53
[10 empty] | Owen Klyed | 2012-06-08 17:15 | Send invoice to customer: [*Invoices*¦http://beem4business/open invoices/download]
Beem for Business | B4B-24 | Video feed | Medium | Dalia Lens | Done | Done | 2012-05-17 12:54 | 2012-06-06 | 2012-06-09 | Owen Klyed | 2012-06-08 16:53 | Will the technical ppl be attending the meeting tomorrow? I'l have a bunch of requests
[10 empty] | Owen Klyed | 2012-06-08 17:15 | Hooray…I'll be there…
Beem for Business | B4B-23 | Video sharing feature | Low | Robert Mongose | To Do |  | 2012-05-17 12:53 | 2012-06-02 | 2012-06-06 | Levente Szabo | 2012-05-22 | Just so you know, there's been a decision about intgrations and *Snapchat is not one of those*, so we can stop looking their API documentation.
Beem for Business | B4B-22 | Video recording feature | Medium | Robert Mongose | To Do |  | 2012-05-17 12:52 | 2012-05-29 | 2012-06-02 | Robert Mongose | 2012-05-30 | Hey you Spielbergs, are you ready to test the greatest feature of [*the app*¦http://beem4business/download]?
Beem for Business | B4B-21 | Implement MVP functions | Medium | Levente Szabo | Done | Done | 2012-05-17 12:40 | 2012-05-10 | 2012-05-26 | Levente Szabo | 2012-05-26 | _Eric Ries_ is in town!! He is one of our users, let's catch him for a customer interview!
Beem for Business | B4B-20 | Log-in form | Medium | Robert Mongose | To Do |  | 2012-05-16 11:04 | 2012-05-24 | 2012-05-26 | Dalia Lens | 2012-06-14 | [~Robert]Check out the templates I made today!
Beem for Business | B4B-19 | Sign-up form | Medium | Levente Szabo | In Progress |  | 2012-05-16 11:03 | 2012-05-22 | 2012-05-24 |  | 2012-05-29
Beem for Business | B4B-18 | Tutorial section | Medium | Dalia Lens | Done | Done | 2012-05-16 10:59 | 2012-05-16 | 2012-05-22 | Dalia Lens | 2012-06-20 | I'm finishing up the wording of the tutorial. Can I have someone to review it? Come on guys, volunteer!
Beem for Business | B4B-17 | Set up cloud hosting | Low | Robert Mongose | Done | Done | 2012-05-16 10:54 | 2012-05-15 | 2012-05-15 | Klyed Owens | 2012-06-14 | [~Robert], I think I'll need some help with setting u the AWS environment. Can you help me out when you have some time?
Beem for Business | B4B-16 | Set up Dev Environment | Medium | Robert Mongose | Done | Done | 2012-05-16 10:52 | 2012-05-11 | 2012-05-15 |  | 2012-05-29
Beem for Business | B4B-15 | Set up DB | Medium | Robert Mongose | Done | Done | 2012-05-16 10:51 | 2012-05-10 | 2012-05-10 |  | 2012-06-20
Beem for Business | B4B-14 | Create landing page | Medium | Dalia Lens | To Do |  | 2012-05-14 21:41 | 2012-06-20 | 2012-06-22 | Levente Szabo | 2012-06-21 | Guys, we will work with the exact same designer team than last time so you know what to expect. Your invitation for a kick-off meeting will follow.
Beem for Business | B4B-8 | Design Feedback (1.) | Medium | Dalia Lens | Done | Done | 2012-05-14 19:29 | 2012-05-09 | 2012-05-09 | Dalia Lens | 2012-05-18 18:11 | Great! :) I'll bring my [*latest sketches*¦http://behance.com/dalial] to the meeting!
[10 empty] | Levente Szabo | 2012-05-19 11:46 | That's awesome [~dalia] thank you and please come prepared to present them.
Beem for Business | B4B-13 | Decision on landing page design | Medium | Dalia Lens | In Progress |  | 2012-05-14 21:36 | 2012-06-19 | 2012-06-19
Beem for Business | B4B-12 | A/B test landing page | Low | Dalia Lens | In Progress |  | 2012-05-14 19:50 | 2012-06-05 | 2012-06-19
Beem for Business | B4B-11 | Landing page copy | Medium | Dalia Lens | In Progress |  | 2012-05-14 19:47 | 2012-05-31 | 2012-06-02
Beem for Business | B4B-10 | Design Feedback (3.) | Medium | Dalia Lens | To Do |  | 2012-05-14 19:42 | 2012-05-23 | 2012-05-23
Beem for Business | B4B-9 | Design Feedback (2.) | Medium | Dalia Lens | Done | Done | 2012-05-14 19:36 | 2012-05-16 | 2012-05-16
Beem for Business | B4B-7 | Graphic designer briefing (1.) | High | Dalia Lens | Done | Done | 2012-05-14 19:18 | 2012-06-02 | 2012-06-02
Beem for Business | B4B-6 | MVP functionality | High | Owen Klyed | Done | Done | 2012-05-14 18:50 | 2012-05-31 | 2012-06-02
Beem for Business | B4B-5 | Traditional market research | Lowest | Owen Klyed | Done | Done | 2012-05-14 18:48 | 2012-05-16 | 2012-05-30
Beem for Business | B4B-4 | Validation landing page | Highest | Owen Klyed | Done | Done | 2012-05-14 18:44 | 2012-05-17 | 2012-05-17
Beem for Business | B4B-3 | Customer interviews | Highest | Owen Klyed | Done | Done | 2012-05-14 18:40 | 2012-05-16 | 2012-05-30
Beem for Business | B4B-1 | Secure and buy the domain name | Low | Dalia Lens | Done | Done | 2012-05-11 11:50 | 2012-05-16 | 2012-05-16
42