## Issue Navigator
Key | Project | Summary | Status | Created | Updated | Resolved | Worklog Author | Worklog Time | Time Spent (h) | Worklog Comment
BFB-38 | Beem for Business | Historical analysis | Done | 2012-05-19 13:44 | 2012-12-06 14:47 | 2012-05-22 11:19 | Levente Szabo | 2012-08-16 16:13 | 59.2 | Researching archived online content about the target market
BFB-37 | Beem for Business | Online research | Done | 2012-05-19 13:44 | 2012-12-05 11:15 | 2012-05-22 14:46 | Levente Szabo | 2012-08-16 16:13 | 80
BFB-36 | Beem for Business | Phone interviews | Done | 2012-05-19 13:38 | 2012-12-06 14:45 | 2012-05-22 11:18 | Casey Ford | 2012-05-25 16:39 | 83 | Conducting phone interviews, using the previously purchased database
BFB-36 | Beem for Business | Phone interviews | Done | 2012-05-19 13:38 | 2012-12-06 14:45 | 2012-05-22 11:18 | Casey Ford | 2012-05-24 14:44 | 2 | Purchasing relevant phone database and merging with our own existing database
BFB-35 | Beem for Business | In person interviews | Done | 2012-05-19 13:36 | 2012-12-05 11:19 | 2012-07-18 15:51 | Casey Ford | 2012-05-16 10:09 | 80 | In-person customer interviews conducted among the previously signed-up users.
BFB-30 | Beem for Business | Set up FB group for beta testers | To Do | 2012-05-17 13:06 | 2012-12-06 14:21 |  | Levente Szabo | 2012-08-16 16:16 | 10 | Registering account, uploading profile data
BFB-30 | Beem for Business | Set up FB group for beta testers | To Do | 2012-05-17 13:06 | 2012-12-06 14:21 |  | Levente Szabo | 2012-08-17 14:17 | 11 | Setting up group for beta testers, building out network on FB
BFB-27 | Beem for Business | Set up Mailchimp | In Progress | 2012-05-17 12:58 | 2012-12-06 14:58 |  | Nigel Simmons | 2012-08-09 11:28 | 5 | Campaign copywriting
BFB-27 | Beem for Business | Set up Mailchimp | In Progress | 2012-05-17 12:58 | 2012-12-06 14:58 |  | Nigel Simmons | 2012-07-31 14:51 | 0.5 | Creating Mailchimp account
BFB-27 | Beem for Business | Set up Mailchimp | In Progress | 2012-05-17 12:58 | 2012-12-06 14:58 |  | Nigel Simmons | 2012-08-02 14:52 | 1.25 | Creating campaigns, campaign workflows
BFB-27 | Beem for Business | Set up Mailchimp | In Progress | 2012-05-17 12:58 | 2012-12-06 14:58 |  | Nigel Simmons | 2012-08-03 14:53 | 1.5 | Meeting with UI team to decide on Mailchimp letter templates
BFB-27 | Beem for Business | Set up Mailchimp | In Progress | 2012-05-17 12:58 | 2012-12-06 14:58 |  | Levente Szabo | 2012-08-04 14:53 | 0.58333 | Setting up automatic reporting from Mailchimp for management
BFB-26 | Beem for Business | Set up Hootsuite account | To Do | 2012-05-17 12:57 | 2012-07-14 14:19
BFB-24 | Beem for Business | Video feed | Done | 2012-05-17 12:54 | 2012-12-15 15:15 | 2012-07-18 15:51 | Levente Szabo | 2012-06-15 16:30 | 24 | Creating test recordings
BFB-24 | Beem for Business | Video feed | Done | 2012-05-17 12:54 | 2012-12-15 15:15 | 2012-07-18 15:51 | Levente Szabo | 2012-12-15 | 3 | Editing test recording, testing upload speed
BFB-23 | Beem for Business | Video sharing feature | To Do | 2012-05-17 12:53 | 2012-12-05 11:02
BFB-22 | Beem for Business | Video recording feature | To Do | 2012-05-17 12:52 | 2012-12-05 11:01 |  | Levente Szabo | 2012-05-29 16:30 | 32 | Testing recording in night-mode
BFB-21 | Beem for Business | Implement MVP functions for app | Done | 2012-05-17 12:40 | 2012-12-06 14:16 | 2012-06-09 10:09 | Levente Szabo | 2012-05-10 10:17 | 100.5667 | Implementation and feature testing for features: sign-up, login, video uploading, video streaming
BFB-20 | Beem for Business | Log-in form | To Do | 2012-05-16 11:04 | 2012-12-05 11:32
BFB-19 | Beem for Business | Sign-up form | Done | 2012-05-16 11:03 | 2012-12-05 11:32 | 2012-09-20 16:50 | Levente Szabo | 2012-06-22 16:31 | 16
BFB-18 | Beem for Business | Tutorial section | Done | 2012-05-16 10:59 | 2012-12-05 11:40 | 2012-05-22 14:46 | Levente Szabo | 2012-05-16 16:58 | 40
BFB-17 | Beem for Business | Set up cloud hosting | Done | 2012-05-16 10:54 | 2012-08-09 11:39 | 2012-05-22 14:45
BFB-16 | Beem for Business | Set up Dev Environment | Done | 2012-05-16 10:52 | 2012-12-06 14:39 | 2012-05-22 14:44 | Levente Szabo | 2012-08-17 14:35 | 0.55 | Registering account with Gitlab.com
BFB-16 | Beem for Business | Set up Dev Environment | Done | 2012-05-16 10:52 | 2012-12-06 14:39 | 2012-05-22 14:44 | Levente Szabo | 2012-08-30 14:36 | 1 | Private repo created on Gitlab.com
BFB-16 | Beem for Business | Set up Dev Environment | Done | 2012-05-16 10:52 | 2012-12-06 14:39 | 2012-05-22 14:44 | Levente Szabo | 2012-09-07 14:37 | 0.86667 | Workflows created and configured on Gitlab.com repositories
BFB-15 | Beem for Business | Set up DB | Done | 2012-05-16 10:51 | 2012-12-06 14:22 | 2012-05-22 14:44 | Levente Szabo | 2012-12-06 14:21 | 3 | Installing and configuring MySQL database
BFB-14 | Beem for Business | Create landing page | To Do | 2012-05-14 21:41 | 2012-12-05 11:29 |  | Levente Szabo | 2012-08-16 16:29 | 21.8 | Developing landing page, image viewer, sign-up feature
BFB-13 | Beem for Business | Decision on landing page design | Done | 2012-05-14 21:36 | 2012-12-05 11:25 | 2012-09-20 16:50
BFB-12 | Beem for Business | A/B test landing page | Done | 2012-05-14 19:50 | 2012-12-06 14:51 | 2012-09-20 16:50 | Levente Szabo | 2012-09-04 14:48 | 0.0083333 | Creating Unbounce account
BFB-12 | Beem for Business | A/B test landing page | Done | 2012-05-14 19:50 | 2012-12-06 14:51 | 2012-09-20 16:50 | Levente Szabo | 2012-09-06 14:49 | 2.75 | Creating landing page versions for testing with different copy language
BFB-12 | Beem for Business | A/B test landing page | Done | 2012-05-14 19:50 | 2012-12-06 14:51 | 2012-09-20 16:50 | Levente Szabo | 2012-09-07 14:50 | 80 | Testing landing page with 2 versions
BFB-11 | Beem for Business | Landing page copy | Done | 2012-05-14 19:47 | 2012-12-06 14:48 | 2012-09-20 16:50 | Levente Szabo | 2012-05-31 10:19 | 16 | Copy writing for the final landing page
BFB-11 | Beem for Business | Landing page copy | Done | 2012-05-14 19:47 | 2012-12-06 14:48 | 2012-09-20 16:50 | Levente Szabo | 2012-06-02 14:47 | 77.75 | More copy for the landing page, corrected after meeting with UI experts
BFB-10 | Beem for Business | Design Feedback (3.) | Done | 2012-05-14 19:42 | 2012-12-05 11:38 | 2012-09-20 16:49
BFB-9 | Beem for Business | Design Feedback (2.) | Done | 2012-05-14 19:36 | 2012-12-05 11:22 | 2012-07-13 18:02
BFB-8 | Beem for Business | Design Feedback (1.) | In Progress | 2012-05-14 19:29 | 2012-12-05 11:13 |  | Levente Szabo | 2012-05-08 11:40 | 1.5 | Finalizing the agenda, securing meeting room and equipment
BFB-8 | Beem for Business | Design Feedback (1.) | In Progress | 2012-05-14 19:29 | 2012-12-05 11:13 |  | Levente Szabo | 2012-05-05 11:42 | 0.5 | Checked with the client, sent out calendar invitations for the meeting
BFB-5 | Beem for Business | Traditional market research | Done | 2012-05-14 18:48 | 2012-12-06 14:43 | 2012-05-22 15:01 | Levente Szabo | 2012-07-16 14:32 | 36.75 | Purchasing and analyzing market research data
BFB-5 | Beem for Business | Traditional market research | Done | 2012-05-14 18:48 | 2012-12-06 14:43 | 2012-05-22 15:01 | Levente Szabo | 2012-07-18 14:41 | 16.6667 | Articles and industry news about the beem4biz target market
BFB-5 | Beem for Business | Traditional market research | Done | 2012-05-14 18:48 | 2012-12-06 14:43 | 2012-05-22 15:01 | Levente Szabo | 2012-09-04 14:42 | 21.5 | Financial analysis and revenue structure analysis of legacy industry players
BFB-4 | Beem for Business | Landing page validation | Done | 2012-05-14 18:44 | 2012-12-12 17:10 | 2012-05-24 14:22 | Levente Szabo | 2012-09-11 14:33 | 4.9 | Meeting to analyze the A/B testing data and further conclusions and decide about landing page launch date
BFB-3 | Beem for Business | Customer interviews | Done | 2012-05-14 18:40 | 2012-12-05 11:23 | 2012-05-19 16:04 | Levente Szabo | 2012-05-14 22:13 | 120.9
BFB-1 | Beem for Business | Secure and buy the domain name | Done | 2012-05-11 11:50 | 2012-05-22 14:45 | 2012-05-22 14:45
43 | [8 empty] | 956.0417