## Issue Navigator
Key | T | P | Summary | Status | Assignee | SAFe Job Size | Cost of Delay ($) | Due
PF-69 | Program | Low | 1 Fast Charging Equipment Development | Under development |  | 30 | 234000 | 2020-08-10
PF-2 | Initiative | Highest | 1.1 Charging infrastructure development | Under development | Zoe Barnes |  | 1400000 | 2020-06-08
| Folder |  | 1.1.1 Charging Equipment by markets
PF-74 | Epic | Low | 1.1.1.1 Consumer Charging Products | Under development |  | 22 | 645900 | 2020-06-08
| Folder |  | 1.1.1.1.1 Home charging
PF-21 | Story | Highest | 1.1.1.1.1.1 As a homeowner, I want to setup a home charging station | Under development | Robert Mongose | 21 | 155600 | 2020-06-18
PF-30 | Task | Highest | 1.1.1.1.1.1.1 Setup bi-directional energy meters | Under installation | Robert Mongose | 2 | 6000 | 2020-04-29
PF-29 | Task | Highest | 1.1.1.1.1.1.2 Test capacity to deliver full output power continuously | Under development | Bob Mitchell | 4 | 3000 | 2020-06-06
PF-28 | Task | Highest | 1.1.1.1.1.1.3 Residual current circuit brakers | Under installation | Robert Mongose | 2 | 19883 | 2020-04-29
PF-27 | Task | Highest | 1.1.1.1.1.1.4 Fuse switch connector | Done | Bob Mitchell | 4 | 19400 | 2020-06-08
PF-75 | Epic | Low | 1.1.1.2 Business Charging Products | Under installation |  | 26 | 236000 | 2020-07-06
| Folder |  | 1.1.1.2.1 Office Building charging
PF-20 | Story | Highest | 1.1.1.2.1.1 As a business owner, I want to learn about business charging solutions | Under development | Casey Ford | 6 | 95600 | 2020-06-18
PF-55 | Task | Low | 1.1.1.2.1.1.1 Gauging employee interest through a survey | Done | Bob Mitchell | 2 | 3200 | 2020-06-11
PF-26 | Task | Highest | 1.1.1.2.1.1.2 CP4000 family charing solution for up to 150 customers | Under development | Bob Mitchell | 4 | 19400 | 2020-06-06
PF-38 | Task | Highest | 1.1.1.2.1.1.3 Access to drivers and network | Under development | Casey Ford | 4 | 23870 | 2020-06-11
CHS-11 | Sub-task | Highest | 1.1.1.2.1.1.3.1 New driver compensation options | In progress | Robert Mongose | 1 | 19883 | 2020-04-29
| Folder |  | 1.1.1.2.2 Commercial Property charging
PF-19 | Story | Highest | 1.1.1.2.2.1 As a commercial property operator, I want to provide EV fast charging spots for customers | Under development | Casey Ford | 4 | 256000 | 2020-06-18
CHS-4 | Task | Highest | 1.1.1.2.2.1.1 Designing and planning of site | Done | Bob Mitchell | 2 | 25000 | 2020-04-29
CHS-7 | Task | Highest | 1.1.1.2.2.1.2 Installation of charging stations | In progress | Robert Mongose | 6 | 120600 | 2020-06-06
PF-35 | Task | Low | 1.1.1.2.2.1.2.1 CP4100 Family for commercial properties above 1000 sqm | Under development | Casey Ford | 2 | 45000 | 2020-04-29
CHS-8 | Task | High | 1.1.1.2.2.1.2.2 CP4300 family for properties above 2500 sqm | In progress | Zoe Barnes | 4 | 19883 | 2020-06-08
PF-51 | Task | Low | 1.1.1.2.2.2 Incentives for property owners | Under development | Casey Ford | 6 | 3200 | 2020-06-06
PF-50 | Task | Medium | 1.1.1.2.2.3 Equip/build new parking spots with charging outlets | Done | Robert Mongose | 8 | 3200 | 2020-06-13
PF-36 | Task | Medium | 1.1.1.2.2.4 Product warranty | Under development | Bob Mitchell | 4 | 19400 | 2020-04-29
PF-71 | Program | Low | 2 Public Roads Products and Continuous Services | Under development |  | 31 | 150000 | 2020-07-08
PF-70 | Initiative | Low | 2.1 Public Charging Equipment Development | Under development |  | 12 | 23890 | 2020-07-16
PF-3 | Epic | Highest | 2.1.1 Charging operations | Under development | Robert Mongose | 18 | 650450 | 2020-06-08
| Folder |  | 2.1.1.1 City charging hub
PF-17 | Story | Highest | 2.1.1.1.1 As a public trasportation provider, I want automated fast charging for heavy vehicles | To Do | Casey Ford | 9 | 43780 | 2020-06-18
PF-54 | Task | Lowest | 2.1.1.1.1.1 Build out automated rooftop connection option | Testing | Casey Ford | 6 | 19400 | 2020-06-08
PF-53 | Task | Low | 2.1.1.1.1.2 Install ultra-fast DC charging platform for public transport | Done | Zoe Barnes | 4 | 250000 | 2020-06-11
PF-42 | Task | Medium | 2.1.1.1.1.3 Single vehicle charge up to 500 kilowatts | Under development | Bob Mitchell | 8 | 19883 | 2020-04-29
PF-34 | Task | Lowest | 2.1.1.1.2 Connect up the power distribution blocks to power service provider | To Do | Bob Mitchell | 10 | 25000 | 2020-04-29
| Folder |  | 2.1.1.2 Intercity highway charging stations
PF-37 | Task | Highest | 2.1.1.2.1 Roaming and interoperability | Under development | Zoe Barnes | 6 | 25000 | 2020-06-06
PF-49 | Task | Medium | 2.1.1.2.2 Support charging in towns and remote areas | To Do | Casey Ford | 2 | 450900 | 2020-04-29
PF-58 | Sub-task | Lowest | 2.1.1.2.2.1 Propose the list of towns with population under 10000 | To Do | Bob Mitchell | 10 | 19400 | 2020-06-08
CHS-3 | Epic | Highest | 2.1.2 Connected services | In progress | Zoe Barnes | 11 | 235000 | 2020-06-08
PF-16 | Story | Highest | 2.1.2.1 As a developer, I want access to APIs and ChargePool web tools | To Do | Robert Mongose | 7 | 23450 | 2020-06-18
PF-40 | Task | Lowest | 2.1.2.1.1 Start a connected Network Operation Center (NOC) | Under development | Bob Mitchell | 2 | 250000 | 2020-04-29
CHS-14 | Task | Medium | 2.1.2.1.2 Offer advanced web tools to operate and monitor chargers in real-time | Under installation | Casey Ford | 8 | 19883 | 2020-06-13
CHS-13 | Task | Low | 2.1.2.1.3 Basic Demand/Response API to dynamically manage the input power of a charger | In progress | Bob Mitchell | 4 | 34910 | 2020-06-08
CHS-16 | Task | Low | 2.1.2.1.4 Service API with technical status data from the charger | Under installation | Zoe Barnes | 2 | 4500 | 2020-06-11
CHS-15 | Task | High | 2.1.2.1.5 Open ChargePool Protocol (OCPP) API to integrate with back-office systems | Under installation | Zoe Barnes | 10 | 15200 | 2020-04-29
CHS-5 | Task | Highest | 2.1.2.2 Initial Site Setup | In progress | Robert Mongose | 6 | 9800 | 2020-06-11
CHS-10 | Sub-task | High | 2.1.2.2.1 Initial Activation and Configuration | Under installation | Casey Ford | 10 | 4500 | 2020-06-06
CHS-6 | Task | Highest | 2.1.2.3 Introcude a Standard Warranty package | In progress | Bob Mitchell | 2 | 4678 | 2020-04-29
CHS-9 | Sub-task | High | 2.1.2.3.1 Implement ChargePool Assure with early customers | In progress | Casey Ford | 10 | 15200 | 2020-06-11
PF-57 | Sub-task | Medium | 2.1.2.3.2 Coverage of labor for repairs | To Do | Robert Mongose | 3 | 19883 | 2020-06-08
PF-46 | Task | Lowest | 2.1.2.4 24X7 proactive station health monitoring | Under development | Casey Ford | 18 | 123560 | 2020-06-08
PF-43 | Task | Lowest | 2.1.2.4.1 Detailed reporting feature for premium customers | To Do | Casey Ford | 2 | 19883 | 2020-04-29
PF-56 | Sub-task | Medium | 2.1.2.4.1.1 Capturing and analyzing EVSE utilization data | Under development | Bob Mitchell | 10 | 19400 | 2020-06-06
PF-45 | Task | Low | 2.1.2.4.2 Monthly reports of station’s performance metrics | To Do | Robert Mongose | 4 | 4500 | 2020-06-11
PF-44 | Task | High | 2.1.2.4.3 Detailed quarterly reports of stations performance metrics | Under development | Robert Mongose | 2 | 34910 | 2020-04-29
PF-41 | Task | Low | 2.1.2.5 Express Plus platform shares power intelligently among two stations | To Do | Bob Mitchell | 6 | 19400 | 2020-06-13
PF-72 | Program | Low | 3 Contractual Services | Under development |  | 14 | 416793 | 2020-07-13
PF-73 | Initiative | Low | 3.1 Support and Maintenance | Under development |  | 14 | 4164 | 2020-07-21
CHS-2 | Epic | Highest | 3.1.1 Charger maintenance | In progress | Robert Mongose | 12 | 345000 | 2020-06-08
CHS-12 | Story | Highest | 3.1.1.1 As a ChargePool customer, I want a reliable ongoing support contract | In progress | Bob Mitchell | 5 | 12500 | 2020-06-18
PF-48 | Task | Highest | 3.1.1.1.1 Unlimited software configuration changes | Under development | Casey Ford | 8 | 19883 | 2020-04-29
PF-47 | Task | Lowest | 3.1.1.1.2 Proactive dispatch of repair technicians when required | Done | Robert Mongose | 2 | 4500 | 2020-06-08
PF-52 | Task | Lowest | 3.1.1.1.3 98% annual uptime guarantee | Under development | Bob Mitchell | 4 | 34910 | 2020-06-06
64 | [5 empty] | 456 | 6748129
Created at 02/Sep/20 3:24 PM by Levente Szabo with Better Excel Exporter for Jira
help »